## Sheet1
HRM Measurement
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research ACDM for architecture process | Medium | Architecture | Tan Tran | 2 | 2011-10-07 | 8 | 2 | 100 | 2011-09-26
2 | Document Concept of Operation | Medium | RE | Tan Tran | 3 | 2011-10-11 | 3 | 2.5 | 100
3 | Review HRM requirement | Medium | RE | Tan Tran | 3 | 2011-10-12 | 3 | 1.5 | 100
4 | Analyse Requirement - Draw mindmap of PIM | High | RE | Tan Tran | 5 | 2011-10-29 | 16 | 24 | 100
5 | Document project plan- Methodology Introduction | High | Management | Tan Tran | 9 | 2011-11-27 | 3 | 4.5 | 100
6 | Programming "Manage Catalog" | Very High | Implementation | Tan Tran | 18 | 2012-01-26 | 70 | 61 | 100
8 | Design database | Medium | Architecture | Tan Tran | 17 | 2012-01-21 | 15 | 22.5 | 100
9 | Document Architecture Driver Document- Quality Attribute | High | Architecture | Tan Tran | 15 | 2012-01-08 | 20 | 16 | 100
10 | Review ConsOpt | Medium | RE | Tan Tran | 6 | 2011-11-03 | 5 | 3 | 100
11 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tan Tran | 16 | 2012-01-13 | 35 | 20 | 100
12 | Document SAD | Very High | Architecture | Tan Tran | 17 | 2012-01-16 | 35 | 32.5 | 100
13 | Review SAD | High | Architecture | Tan Tran | 17 | 2012-01-18 | 5 | 3 | 100
14 | Risk analysis in implementation | Very High | Management | Tan Tran | 17 | 2012-01-17 | 6 | 6.5 | 100
15 | Write test cases | Very High | Testing | Tan Tran | 12 | 2011-12-13 | 5 | 5 | 50
16 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tuong Nguyen | -5830 |  | 5 | 3.5 | 100
17 | Research ACDM for architecture process | Medium | Architecture | Tuong Nguyen | -5830 |  | 8 | 6.5 | 100
18 | Document Scenarios for "Training Management" | Low | RE | Tuong Nguyen | -5830 |  | 1 | 2 | 100
19 | Concept Operation | Very High | RE | Tuong Nguyen | -5830 |  | 7 | 5 | 100
20 | Prepare for Architecture Driver | Medium | Architecture | Tuong Nguyen | 6 | 2011-11-03 | 2 | 3 | 100
21 | Update Architecture Driver | High | Architecture | Tuong Nguyen | -5830 |  | 4 | 5 | 50
22 | Design Database | High | Architecture | Tuong Nguyen | -5830 |  | 6 | 3 | 50
23 | Write Architecture Design | Very High | Architecture | Tuong Nguyen | -5830 |  | 6 | 5.5 | 100
24 | Program "Nghề nghiệp" Interface | Medium | Implementation | Tuong Nguyen | 11 | 2011-12-09 | 2 | 3.5 | 100
25 | Review SAD | Medium | Architecture | Tuong Nguyen | -5830 |  | 5 | 3.5 | 50
26 | Design System Context | Medium | Architecture | Tuong Nguyen | -5830 |  | 4 | 2 | 100
27 | Doc Project Plan | Very High | Management | Nhung Huyng | -5830 |  | 35 | 35 | 100
28 | Doc Detail Plan | Very High | Management | Nhung Huyng | -5830 |  | 6 | 6 | 100
29 | Doc Weekly report for mentor | Medium | Management | Nhung Huyng | -5830 |  | 42 | 42 | 100
30 | Research about rule for team member | Very High | Management | Nhung Huyng | -5830 |  | 5 | 5 | 100
31 | Research about team 360 review on web | High | Management | Nhung Huyng | -5830 |  | 8 | 8 | 100
32 | Research about Risk Management Process and Template | High | Management | Nhung Huyng | 3 | 2011-10-11 | 7 | 6 | 100
33 | Doc risk management plan and create template | High | Management | Nhung Huyng | 3 | 2011-10-13 | 5 | 5.5 | 100
34 | Add and review Risk category | Medium | Management | Nhung Huyng | 12 | 2011-12-12 | 4 | 2.5 | 100
35 | Doc Concep Operation | Very High | RE | Nhung Huyng | 7 | 2011-11-07 | 15 | 10.5 | 50
36 | Doc InformationCategory in Concept Operation | Medium | Management | Nhung Huyng | 15 | 2012-01-02 | 13 | 12.5 | 50
37 | Review and fix Concept Operation document | Very High | RE | Nhung Huyng | 11 | 2011-12-11 | 11 | 10 | 50
38 | Doc Functional Requirement in SRS, business rules | Very High | RE | Nhung Huyng | 12 | 2011-12-12 | 3 | 1.5 | 50
39 | Review and fix SRS | Very High | RE | Nhung Huyng | 12 | 2011-12-12 | 2 | 1.5 | 50
40 | Add new Risk category | Medium | Management | Nhung Huyng | 13 | 2011-12-19 | 1 | 1 | 100
41 | Implement Interface: Extend Information and Detail Information | High | Management | Nhung Huyng | 11 | 2011-12-11 | 5 | 4 | 50
42 | Doc artifact about Change Management Plan | High | Management | Nhung Huyng | 16 | 2012-01-13 | 4 | 4 | 100
43 | Research about Change management | High | Management | Nhung Huyng | 16 | 2012-01-13 | 4 | 4 | 100
44 | Report and doc Change management log and Change Request for CR01 | High | Management | Nhung Huyng | 16 | 2012-01-13 | 4 | 4 | 100
45 | Define Detail Design process | High | Detail Design | Dang Nguyen | -5830 |  | 2 | 1.5 | 100
46 | Doc Detail Design process | Low | Detail Design | Dang Nguyen | -5830 |  | 0.5 | 0.5 | 100
47 | Concept of Operation: document Proposed System or Situation | Very High | RE | Dang Nguyen | -5830 |  | 10 | 11.5 | 100
48 | Concept of Operation: document Current System or Situation | High | RE | Dang Nguyen | -5830 |  | 4 | 5 | 100
49 | Read, Review and Draw Form of customer | Medium | RE | Dang Nguyen | -5830 |  | 3 | 3 | 100
50 | Test Plan: ENTRANCE & EXIT CRITERIA | High | Testing | Dang Nguyen | -5830 |  | 2 | 2 | 100
51 | Project .Plan: Project Quality Plan | High | Management | Dang Nguyen | -5830 |  | 1 | 1 | 100
52 | Describe Quality Attribute | High | RE | Dang Nguyen | -5830 |  | 6 | 9 | 100
53 | draw current system overview | High | RE | Dang Nguyen | -5830 |  | 7 | 7 | 100
54 | List Use Case | Medium | RE | Dang Nguyen | -5830 |  | 1.5 | 1.5 | 100
55 | draw Register the hour for teacher process | Medium | RE | Dang Nguyen | -5830 |  | 1 | 1 | 100
56 | Draw Use Case | High | RE | Dang Nguyen | -5830 |  | 6 | 7 | 100
57 | Describe Use Case | High | RE | Dang Nguyen | -5830 |  | 5 | 7 | 100
58 | rework: System feature | High | RE | Dang Nguyen | -5830 |  | 2 | 2 | 100
59 | review SRS | Medium | RE | Dang Nguyen | -5830 |  | 3 | 2.5 | 100
60 | design Detail Design template | Medium | Detail Design | Dang Nguyen | -5830 |  | 3 | 4 | 100
61 | Implement Interface: manage major | Medium | Implementation | Dang Nguyen | -5830 |  | 3 | 3 | 100
62 | review Use Case Description | Medium | RE | Dang Nguyen | -5830 |  | 1 | 1 | 100
63 | Plan Detail Design | High | Detail Design | Dang Nguyen | -5830 |  | 3 | 3 | 100
64 | Decribe Detail design Introduction | Low | Detail Design | Dang Nguyen | -5830 |  | 1 | 1 | 100
65 | Implement interface: Working Progress and Labor Union | Medium | Implementation | Dang Nguyen | -5830 |  | 7 | 7 | 100
66 | Test Case : Working Progress and Labor Union | Medium | Testing | Dang Nguyen | -5830 |  | 2 | 3 | 100
67 | Design Interface: Detail Information | Very High | Implementation | Dang Nguyen | -5830 |  | 12 | 9 | 70
69 | Write document content for meeting with customer | Medium | RE | Loc Phan | 1 | 2011-09-30 |  | 3 | 100
70 | List questions for meeting with customer | High | RE | Loc Phan | 1 | 2011-09-30 |  | 4 | 100
74 | Research about Design Process | Medium | RE | Loc Phan | 2 | 2011-10-05 |  | 5 | 100
75 | List questions and answer for meeting with customer | Medium | RE | Loc Phan | 2 | 2011-10-05 |  | 2 | 100
77 | Document list questions and answer | High | RE | Loc Phan | 2 | 2011-10-06 |  | 4 | 100
78 | Write introduction for ConceptOperation | Low | RE | Loc Phan | 2 | 2011-10-07 |  | 2 | 100
79 | Update part 6 for ConceptOperation | High | RE | Loc Phan | 5 | 2011-10-30 |  | 3 | 100
80 | Update part 3 for ConceptOperation | High | RE | Loc Phan | 6 | 2011-10-31 |  | 2 | 100
81 | Group catalog (from customer requirement) | Medium | RE | Loc Phan | 6 | 2011-11-01 |  | 2 | 100
82 | List informations to manage and group its. | Medium | RE | Loc Phan | 6 | 2011-11-04 |  | 1.5 | 100
83 | Document SRS part 2.5; 2.6; 2.7 | High | RE | Loc Phan | 7 | 2011-11-07 |  | 5 | 100
84 | Draw context Diagram and descript context | Medium | RE | Loc Phan | 7 | 2011-11-08 |  | 3 | 100
85 | Update Funtional Requirement and Business Rule | High | RE | Loc Phan | 8 | 2011-11-15 |  | 7 | 100
86 | Descript Use-case | High | RE | Loc Phan | 9 | 2011-11-24 |  | 8 | 100
87 | Update 2.3, 2.4, 2.6 , 2.7, 5 SRS and Functionlist. | High | RE | Loc Phan | 11 | 2011-12-05 |  | 4 | 100
89 | Update All use-case | High | RE | Loc Phan | 11 | 2011-12-11 |  | 5 | 100
91 | Update Risk Register | Medium | RE | Loc Phan | 12 | 2011-12-18 |  | 3 | 100
92 | Draw activities diagram | Medium | RE | Loc Phan | 19 | 2012-02-02 |  | 6 | 100
93 | Update activities diagram | Medium | RE | Loc Phan | 10 | 2011-12-02 |  | 3 | 100
94 | Prepare content for meeting with customer | Medium | RE | Tung Nguyen | 2 | 2011-10-03 |  | 1 | 100
96 | Write document content for meeting with customer | High | RE | Tung Nguyen | 2 | 2011-10-04 |  | 2 | 100
97 | List questions for meeting with customer | Medium | RE | Tung Nguyen | 2 | 2011-10-05 |  | 2 | 100
98 | Review List of Requirement | Low | RE | Tung Nguyen | 2 | 2011-10-06 |  | 2 | 100
100 | Research about testing Process | High | Testing | Tung Nguyen | 3 | 2011-10-14 |  | 7 | 100
101 | List questions and answer for meeting with customer | Medium | RE | Tung Nguyen | 2 | 2011-10-07 |  | 1 | 100
102 | Create HRM Testing process | Very High | Testing | Tung Nguyen | 7 | 2011-11-08 |  | 11 | 100
103 | Description Phases software testing | High | Testing | Tung Nguyen | 3 | 2011-10-11 |  | 3 | 100
105 | Create Test plan | Very High | Testing | Tung Nguyen | 4 | 2011-10-20 |  | 11 | 100
106 | Create Template Testing | High | Testing | Tung Nguyen | 5 | 2011-10-26 |  | 9 | 100
107 | Document Concept of Operation | Medium | RE | Tung Nguyen | 5 | 2011-10-29 |  | 5 | 100
108 | Review HRM requirement | Medium | RE | Tung Nguyen | 6 | 2011-10-31 |  | 2 | 100
109 | Describe Use Case | High | RE | Tung Nguyen | 10 | 2011-11-29 |  | 8 | 100
110 | Create Template Test case | Medium | Testing | Tung Nguyen | 8 | 2011-11-17 |  | 3 | 100
111 | Update Template Testcase | Medium | Testing | Tung Nguyen | 10 | 2011-12-02 |  | 5 | 100
112 | Write Test Case | High | Testing | Tung Nguyen | 13 | 2011-12-22 |  | 3 | 100
113 | List Risk for Testing | Medium | Testing | Tung Nguyen | 12 | 2011-12-17 |  | 2 | 100
114 | Reparing and Reviewing with customers | High | RE | Quyet Nguyen | -5830 |  | 15 | 10 | 100
115 | Updating requirement process in Project Plan | Very High | RE | Quyet Nguyen | -5830 |  | 5 | 3 | 100
116 | Updating Reflection pappers. | High | RE | Quyet Nguyen | -5830 |  | 6 | 3 | 100
117 | Research SRS document | Medium | RE | Quyet Nguyen | -5830 |  | 10 | 7 | 100
118 | Research some catagolue information | Medium | RE | Quyet Nguyen | -5830 |  | 2 | 2 | 100
119 | Review Catagoloue and Issue in Meeting | High | RE | Quyet Nguyen | -5830 |  | 2 | 2 | 100
120 | Draw business process | High | RE | Quyet Nguyen | -5830 |  | 8 | 6 | 100
121 | Meeting anhd customize Concept document | High | RE | Quyet Nguyen | -5830 |  | 5 | 3.5 | 100
122 | Update Overview SRS document | High | RE | Quyet Nguyen | -5830 |  |  | 3 | 100
123 | Review and Reflect Concept with Customers | Very High | RE | Quyet Nguyen | -5830 |  |  | 18 | 50
125 | Research system function | Medium | RE | Quyet Nguyen | -5830 |  |  | 3 | 50
126 | Establish RE process | High | RE | Quyet Nguyen | 7 | 2011-11-08 |  | 8 | 100
127 | Draw overview for finding and understanding system | High | RE | Quyet Nguyen | -5830 |  |  | 3 | 100
128 | Fix Digram HRM | High | RE | Quyet Nguyen | -5830 |  |  | 2 | 100
129 | Analyze system | High | RE | Quyet Nguyen | -5830 |  |  | 2.5 | 100
130 | Scenario HRM Concept document | High | RE | Quyet Nguyen | -5830 |  |  | 4 | 100
141 | Get requirement | Very High | RE | Quyet Nguyen | -5830 |  | 20 | 22 | 100
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203