## Sheet1
REFLECTION
No. | Difficulties | Solution | Lesson learn | Phase
1 | There are a lot of technologies that need to be researched | Spending more effort for researching about new technologies, e.g. WCF, MVVM,Telerik… | Knowing more about how using the WCF,MVVM, Telerik in architect. | Architecture
2 | The important requirements changes so much | Dealing with the customer to give the specific baseline. | Everything we do need to be baselined to make sure that the customer will not change the requirement | Architecture
3 | Being lack of the experieces in architect, so it is difficult to get the consensus between the architect and detail design | Asking the mentor and the internet for the solution in architect to give the good archiectect. Besides, explaning about the architect and dealing with design team are necessary | Researching more about the new technologies that are used in architect to give the accuracy archiect | Architecture
4 | Being lack of the resource for architect phase, so that it makes the schedule is always behind | "Recruiting" more resource for architect phase | Apportioning the resource in each phase appropriately. Avoiding being lack of resource | Architecture
5 | Requirement phase is always behind the schedule | Dealing with the Requirement team to give the consensus about the key requirement for architect | Communicating with Requirement team to get the key requirements. Avoiding waiting the requirement phase has done and then start the architect phase | Architecture