## Sheet1
HRM Measurement
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research ACDM for architecture process | Medium | Architecture | Tan Tran | 2 | 2011-10-07 | 8 | 2 | 100 | 2011-09-26
2 | Document Concept of Operation | Medium | RE | Tan Tran | 3 | 2011-10-11 | 3 | 2.5 | 100
3 | Review HRM requirement | Medium | RE | Tan Tran | 3 | 2011-10-12 | 3 | 1.5 | 100
4 | Analyse Requirement - Draw mindmap of PIM | High | RE | Tan Tran | 5 | 2011-10-29 | 16 | 24 | 100
5 | Document project plan- Methodology Introduction | High | Management | Tan Tran | 9 | 2011-11-27 | 3 | 4.5 | 100
6 | Programming "Manage Catalog" | Very High | Implementation | Tan Tran | 18 | 2012-01-26 | 70 | 61 | 100
7 | Design database | Medium | Architecture | Tan Tran | 17 | 2012-01-21 | 15 | 22.5 | 100
8 | Document Architecture Driver Document- Quality Attribute | High | Architecture | Tan Tran | 15 | 2012-01-08 | 20 | 16 | 100
9 | Review ConsOpt | Medium | RE | Tan Tran | 6 | 2011-11-03 | 5 | 3 | 100
10 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tan Tran | 16 | 2012-01-13 | 35 | 20 | 100
11 | Document SAD | Very High | Architecture | Tan Tran | 17 | 2012-01-16 | 35 | 32.5 | 100
12 | Review SAD | High | Architecture | Tan Tran | 17 | 2012-01-18 | 5 | 3 | 100
13 | Risk analysis in implementation | Very High | Management | Tan Tran | 17 | 2012-01-17 | 6 | 6.5 | 100
14 | Write test cases | Very High | Testing | Tan Tran | 12 | 2011-12-13 | 5 | 5 | 50
15 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tuong Nguyen | 13 | 2011-12-19 | 5 | 3.5 | 100
16 | Research ACDM for architecture process | Medium | Architecture | Tuong Nguyen | 3 | 2011-10-10 | 8 | 6.5 | 100
17 | Document Scenarios for "Training Management" | Low | RE | Tuong Nguyen | 5 | 2011-10-25 | 1 | 2 | 100
18 | Concept Operation | Very High | RE | Tuong Nguyen | 6 | 2011-11-04 | 7 | 5 | 100
19 | Prepare for Architecture Driver | Medium | Architecture | Tuong Nguyen | 6 | 2011-11-03 | 2 | 3 | 100
20 | Update Architecture Driver | High | Architecture | Tuong Nguyen | 13 | 2011-12-25 | 4 | 5 | 50
21 | Design Database | High | Architecture | Tuong Nguyen | 15 | 2012-01-08 | 6 | 5.5 | 50
22 | Write Architecture Design | Very High | Architecture | Tuong Nguyen | 9 | 2011-11-24 | 6 | 5.5 | 100
23 | Program "Nghề nghiệp" Interface | Medium | Implementation | Tuong Nguyen | 11 | 2011-12-09 | 2 | 3.5 | 100
24 | Review SAD | Medium | Architecture | Tuong Nguyen | 11 | 2011-12-09 | 5 | 3.5 | 50
25 | Design System Context | Medium | Architecture | Tuong Nguyen | 14 | 2011-12-31 | 4 | 2 | 100
26 | Doc Project Plan | Very High | Management | Nhung Huynh | 13 | 2011-12-23 | 35 | 35 | 100
27 | Doc Detail Plan | Very High | Management | Nhung Huynh | 13 | 2011-12-23 | 6 | 6 | 100
28 | Doc Weekly report for mentor | Medium | Management | Nhung Huynh | 21 | 2012-02-15 | 42 | 42 | 100
29 | Research about rule for team member | Very High | Management | Nhung Huynh | 21 | 2012-02-15 | 5 | 5 | 100
30 | Research about team 360 review on web | High | Management | Nhung Huynh | 21 | 2012-02-15 | 8 | 8 | 100
31 | Research about Risk Management Process and Template | High | Management | Nhung Huynh | 3 | 2011-10-11 | 7 | 6 | 100
32 | Doc risk management plan and create template | High | Management | Nhung Huynh | 3 | 2011-10-13 | 5 | 5.5 | 100
33 | Add and review Risk category | Medium | Management | Nhung Huynh | 12 | 2011-12-12 | 4 | 2.5 | 100
34 | Doc Concep Operation | Very High | RE | Nhung Huynh | 7 | 2011-11-07 | 15 | 10.5 | 50
35 | Doc InformationCategory in Concept Operation | Medium | Management | Nhung Huynh | 15 | 2012-01-02 | 13 | 12.5 | 50
36 | Review and fix Concept Operation document | Very High | RE | Nhung Huynh | 11 | 2011-12-11 | 11 | 10 | 50
37 | Doc Functional Requirement in SRS, business rules | Very High | RE | Nhung Huynh | 12 | 2011-12-12 | 3 | 1.5 | 50
38 | Review and fix SRS | Very High | RE | Nhung Huynh | 12 | 2011-12-12 | 2 | 1.5 | 50
39 | Add new Risk category | Medium | Management | Nhung Huynh | 13 | 2011-12-19 | 1 | 1 | 100
40 | Implement Interface: Extend Information and Detail Information | High | Management | Nhung Huynh | 11 | 2011-12-11 | 5 | 4 | 50
41 | Doc artifact about Change Management Plan | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
42 | Research about Change management | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
43 | Report and doc Change management log and Change Request for CR01 | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
44 | Define Detail Design process | High | Detail Design | Dang Nguyen | -5830 |  | 2 | 1.5 | 100
45 | Doc Detail Design process | Low | Detail Design | Dang Nguyen | -5830 |  | 0.5 | 0.5 | 100
46 | Concept of Operation: document Proposed System or Situation | Very High | RE | Dang Nguyen | -5830 |  | 10 | 11.5 | 100
47 | Concept of Operation: document Current System or Situation | High | RE | Dang Nguyen | -5830 |  | 4 | 5 | 100
48 | Read, Review and Draw Form of customer | Medium | RE | Dang Nguyen | -5830 |  | 3 | 3 | 100
49 | Test Plan: ENTRANCE & EXIT CRITERIA | High | Testing | Dang Nguyen | -5830 |  | 2 | 2 | 100
50 | Project .Plan: Project Quality Plan | High | Management | Dang Nguyen | -5830 |  | 1 | 1 | 100
51 | Describe Quality Attribute | High | RE | Dang Nguyen | -5830 |  | 6 | 9 | 100
52 | draw current system overview | High | RE | Dang Nguyen | -5830 |  | 7 | 7 | 100
53 | List Use Case | Medium | RE | Dang Nguyen | -5830 |  | 1.5 | 1.5 | 100
54 | draw Register the hour for teacher process | Medium | RE | Dang Nguyen | -5830 |  | 1 | 1 | 100
55 | Draw Use Case | High | RE | Dang Nguyen | -5830 |  | 6 | 7 | 100
56 | Describe Use Case | High | RE | Dang Nguyen | -5830 |  | 5 | 7 | 100
57 | rework: System feature | High | RE | Dang Nguyen | -5830 |  | 2 | 2 | 100
58 | review SRS | Medium | RE | Dang Nguyen | -5830 |  | 3 | 2.5 | 100
59 | design Detail Design template | Medium | Detail Design | Dang Nguyen | -5830 |  | 3 | 4 | 100
60 | Implement Interface: manage major | Medium | Implementation | Dang Nguyen | -5830 |  | 3 | 3 | 100
61 | review Use Case Description | Medium | RE | Dang Nguyen | -5830 |  | 1 | 1 | 100
62 | Plan Detail Design | High | Detail Design | Dang Nguyen | -5830 |  | 3 | 3 | 100
63 | Decribe Detail design Introduction | Low | Detail Design | Dang Nguyen | -5830 |  | 1 | 1 | 100
64 | Implement interface: Working Progress and Labor Union | Medium | Implementation | Dang Nguyen | -5830 |  | 7 | 7 | 100
65 | Test Case : Working Progress and Labor Union | Medium | Testing | Dang Nguyen | -5830 |  | 2 | 3 | 100
66 | Design Interface: Detail Information | Very High | Implementation | Dang Nguyen | -5830 |  | 12 | 9 | 70
67 | Write document content for meeting with customer | Medium | RE | Loc Phan | 1 | 2011-09-30 | 5 | 3 | 100
68 | List questions for meeting with customer | High | RE | Loc Phan | 1 | 2011-09-30 | 5 | 4 | 100
69 | Research about Design Process | Medium | RE | Loc Phan | 2 | 2011-10-05 | 5 | 5 | 100
70 | List questions and answer for meeting with customer | Medium | RE | Loc Phan | 2 | 2011-10-05 | 3 | 2 | 100
71 | Document list questions and answer | High | RE | Loc Phan | 2 | 2011-10-06 | 2 | 4 | 100
72 | Write introduction for ConceptOperation | Low | RE | Loc Phan | 2 | 2011-10-07 | 2 | 2 | 100
73 | Update part 6 for ConceptOperation | High | RE | Loc Phan | 5 | 2011-10-30 | 5 | 3 | 100
74 | Update part 3 for ConceptOperation | High | RE | Loc Phan | 6 | 2011-10-31 | 2 | 2 | 100
75 | Group catalog (from customer requirement) | Medium | RE | Loc Phan | 6 | 2011-11-01 | 2 | 2 | 100
76 | List informations to manage and group its. | Medium | RE | Loc Phan | 6 | 2011-11-04 | 4 | 1.5 | 100
77 | Document SRS part 2.5; 2.6; 2.7 | High | RE | Loc Phan | 7 | 2011-11-07 | 4 | 5 | 100
78 | Draw context Diagram and descript context | Medium | RE | Loc Phan | 7 | 2011-11-08 | 4 | 3 | 100
79 | Update Funtional Requirement and Business Rule | High | RE | Loc Phan | 8 | 2011-11-15 | 4 | 7 | 100
80 | Descript Use-case | High | RE | Loc Phan | 9 | 2011-11-24 | 6 | 8 | 100
81 | Update 2.3, 2.4, 2.6 , 2.7, 5 SRS and Functionlist. | High | RE | Loc Phan | 11 | 2011-12-05 | 3 | 4 | 100
82 | Update All use-case | High | RE | Loc Phan | 11 | 2011-12-11 | 4 | 5 | 100
83 | Update Risk Register | Medium | RE | Loc Phan | 12 | 2011-12-18 | 3 | 3 | 100
84 | Draw activities diagram | Medium | RE | Loc Phan | 19 | 2012-02-02 | 5 | 6 | 100
85 | Update activities diagram | Medium | RE | Loc Phan | 10 | 2011-12-02 | 2 | 3 | 100
86 | Prepare content for meeting with customer | Medium | RE | Tung Nguyen | 2 | 2011-10-03 |  | 1 | 100
87 | Write document content for meeting with customer | High | RE | Tung Nguyen | 2 | 2011-10-04 |  | 2 | 100
88 | Review List of Requirement | Low | RE | Tung Nguyen | 2 | 2011-10-06 |  | 2 | 100
89 | Research about testing Process | High | Testing | Tung Nguyen | 3 | 2011-10-14 |  | 7 | 100
90 | List questions and answer for meeting with customer | Medium | RE | Tung Nguyen | 2 | 2011-10-07 |  | 1 | 100
91 | Create HRM Testing process | Very High | Testing | Tung Nguyen | 7 | 2011-11-08 |  | 11 | 100
92 | Description Phases software testing | High | Testing | Tung Nguyen | 3 | 2011-10-11 |  | 3 | 100
93 | Create Test plan | Very High | Testing | Tung Nguyen | 4 | 2011-10-20 |  | 11 | 100
94 | Create Template Testing | High | Testing | Tung Nguyen | 5 | 2011-10-26 |  | 9 | 100
95 | Document Concept of Operation | Medium | RE | Tung Nguyen | 5 | 2011-10-29 |  | 5 | 100
96 | Review HRM requirement | Medium | RE | Tung Nguyen | 6 | 2011-10-31 |  | 2 | 100
97 | Describe Use Case | High | RE | Tung Nguyen | 10 | 2011-11-29 |  | 8 | 100
98 | Create Template Test case | Medium | Testing | Tung Nguyen | 8 | 2011-11-17 |  | 3 | 100
99 | Update Template Testcase | Medium | Testing | Tung Nguyen | 10 | 2011-12-02 |  | 5 | 100
100 | Write Test Case | High | Testing | Tung Nguyen | 13 | 2011-12-22 |  | 3 | 100
101 | List Risk for Testing | Medium | Testing | Tung Nguyen | 12 | 2011-12-17 |  | 2 | 100
102 | Reparing and Reviewing with customers | High | RE | Quyet Nguyen | 5 | 2011-10-27 | 15 | 10 | 100
103 | Updating requirement process in Project Plan | Very High | RE | Quyet Nguyen | 21 | 2012-02-15 | 6 | 5 | 100
104 | Updating Reflection pappers. | High | RE | Quyet Nguyen | 17 | 2012-01-16 | 6 | 3 | 100
105 | Research SRS document | Medium | RE | Quyet Nguyen | 6 | 2011-10-31 | 10 | 7 | 100
106 | Research some catagolue information | Medium | RE | Quyet Nguyen | 5 | 2011-10-25 | 2 | 2 | 100
107 | Review Catagoloue and Issue in Meeting | High | RE | Quyet Nguyen | 5 | 2011-10-29 | 2 | 2 | 100
108 | Draw business process | High | RE | Quyet Nguyen | 4 | 2011-10-19 | 8 | 6 | 100
109 | Update Overview SRS document | High | RE | Quyet Nguyen | -10 | 2011-07-11 | 2 | 3 | 100
111 | Research system function | Medium | RE | Quyet Nguyen | 2 | 2011-10-04 | 2 | 3 | 50
112 | Establish RE process | High | RE | Quyet Nguyen | 2 | 2011-10-08 | 5 | 8 | 100
113 | Draw overview for finding and understanding system | High | RE | Quyet Nguyen | 2 | 2011-10-06 | 1 | 3 | 100
114 | Fix Digram HRM | High | RE | Quyet Nguyen | 3 | 2011-10-13 | 3 | 2 | 100
115 | Analyze system | High | RE | Quyet Nguyen | 3 | 2011-10-14 | 2 | 2.5 | 100
116 | Scenario HRM Concept document | High | RE | Quyet Nguyen | 4 | 2011-10-22 | 3 | 4 | 100
118 | Meeting with customers for confirming information after team are analyze customers 's information. | High | RE | Quyet Nguyen | 2 | 2011-10-04 | 3 | 3 | 50
119 | Meeting with customers for reflecting business process | High | RE | Quyet Nguyen | 2 | 2011-10-07 | 3 | 3 | 50
120 | Meeting with customers for getting list information | High | RE | Quyet Nguyen | 5 | 2011-10-28 | 3 | 3 | 50
121 | Meeting with customers for finishing business process | High | RE | Quyet Nguyen | 10 | 2011-11-29 | 3 | 3 | 100
122 | Meeting with customers for getting list information | High | RE | Quyet Nguyen | 9 | 2011-11-26 | 1 | 2 | 50
123 | Meeting with customers for completing list information | High | RE | Quyet Nguyen | 11 | 2011-12-08 |  | 3 | 100
124 | Meeting with customers for adding fuction such as Manage Army Rank, Manage Labor Union, Manage Union Task, Manage Communist Party Task. | High | RE | Quyet Nguyen | 10 | 2011-11-29 | 3 | 3 | 50
125 | Meeting with customers for reviewing new fuctions. | High | RE | Quyet Nguyen | 12 | 2011-12-12 | 3 | 4 | 100
126 | Asking some information are questioning. | Medium | RE | Quyet Nguyen | 13 | 2011-12-19 | 2 | 1 | 100
127 | Capture assuptions based on provided document | Medium | RE | Nguyen Dinh | 2 | 2011-10-03 |  | 4 | 100
128 | Research and do ConOps document | High | RE | Nguyen Dinh | 2 | 2011-10-05 |  | 3 | 100
129 | Review List of Requirement | Low | RE | Nguyen Dinh | 2 | 2011-10-06 |  | 3 | 100
130 | Create HRM requirement process | High | RE | Nguyen Dinh | 2 | 2011-10-07 |  | 2 | 100
131 | Create and update requirement process | Medium | RE | Nguyen Dinh | 3 | 2011-10-10 |  | 2 | 100
132 | Re-construct user's requirement and analysis map | Medium | RE | Nguyen Dinh | 3 | 2011-10-13 |  | 3 | 100
134 | Update section five | Medium | RE | Nguyen Dinh | 5 | 2011-10-27 |  | 1 | 100
135 | Update section seven | Medium | RE | Nguyen Dinh | 5 | 2011-10-30 |  | 2 | 100
136 | Review and fix some bugs on ConsOpt | Medium | RE | Nguyen Dinh | 6 | 2011-10-31 |  | 3.5 | 100
137 | Research and deploy SVN using google code for team | Very High | Management | Nguyen Dinh | 6 | 2011-11-05 |  | 1 | 100
140 | Create initial version for list of functional requirements, business rules, system features | High | RE | Nguyen Dinh | 7 | 2011-11-10 |  | 3 | 100
141 | Review dataflow diagram | Medium | RE | Nguyen Dinh | 7 | 2011-11-10 |  | 1 | 100
142 | Review UC diagram, list of functional requirements, system feature, business rules | Medium | RE | Nguyen Dinh | 8 | 2011-11-17 |  | 2 | 100
143 | Fix version for ConsOpt due to Configuration Management Plan | Low | RE | Nguyen Dinh | 8 | 2011-11-17 |  | 0.5 | 100
144 | Develop UC diagram | Medium | RE | Nguyen Dinh | 8 | 2011-11-20 |  | 3 | 100
145 | Review list of functional requirements | Medium | RE | Nguyen Dinh | 9 | 2011-11-21 |  | 1 | 100
146 | Create UC description template, write description for UC description | Medium | RE | Nguyen Dinh | 9 | 2011-11-22 |  | 1 | 100
147 | Write UC description for UC03.2.2.7 to UC03.2.2.11 | Medium | RE | Nguyen Dinh | 9 | 2011-11-24 |  | 5 | 100
148 | Update UC description for UC03.2.2.7 to UC03.2.2.11 | Medium | RE | Nguyen Dinh | 9 | 2011-11-27 |  | 2 | 100
149 | Review SRS | Medium | RE | Nguyen Dinh | 10 | 2011-11-29 |  | 1 | 100
150 | Research about C# and Silverlight | Very High | Implementation | Nguyen Dinh |  |  |  | 14 | 50
151 | Update section 1 and fix some bugs on entire document | Medium | RE | Nguyen Dinh | 11 | 2011-12-06 |  | 2 | 100
152 | Update section 1 and 2.1, part of 2.2 | Medium | RE | Nguyen Dinh | 11 | 2011-12-07 |  | 1 | 100
153 | Update section 2 | Medium | RE | Nguyen Dinh | 11 | 2011-12-07 |  | 1 | 100
154 | Review and fix some bugs in system feature sheet | Low | RE | Nguyen Dinh | 11 | 2011-12-08 |  | 0.5 | 100
155 | Review 2.3, review and update 2.4, 2.5, 2.6 | Medium | RE | Nguyen Dinh | 11 | 2011-12-09 |  | 1 | 100
156 | Update 2.7 | Medium | RE | Nguyen Dinh | 12 | 2011-12-11 |  | 2 | 100
157 | Gather and translate content table of ConsOpt to English | Low | Management | Nguyen Dinh | 15 | 2012-01-08 |  | 0.5 | 100
158 | Add reflection paper: First version, plus introduction, architect, project management | Medium | Management | Nguyen Dinh | 16 | 2012-01-12 |  | 1 | 100
159 | Review and translate in to English Consopt | Medium | RE | Nguyen Dinh |  |  |  | 4 | 25
160 | Review and update requirement process: process description | Medium | RE | Nguyen Dinh | 22 | 2012-02-20 |  | 1 | 100
161 | Update personal measurement information | Low | Management | Nguyen Dinh | 23 | 2012-02-28 |  | 1 | 100
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180

## Tan Tran
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research ACDM for architecture process | Medium | Architecture | Tan Tran | 2 | 2011-10-07 | 8 | 2 | 100 | 2011-09-26
2 | Document Concept of Operation | Medium | RE | Tan Tran | 3 | 2011-10-11 | 3 | 2.5 | 100
3 | Review HRM requirement | Medium | RE | Tan Tran | 3 | 2011-10-12 | 3 | 1.5 | 100
4 | Analyse Requirement - Draw mindmap of PIM | High | RE | Tan Tran | 5 | 2011-10-29 | 16 | 24 | 100
5 | Review ConsOpt | Medium | RE | Tan Tran | 6 | 2011-11-03 | 5 | 3 | 100
6 | Document project plan- Methodology Introduction | High | Management | Tan Tran | 9 | 2011-11-27 | 3 | 4.5 | 100
7 | Write test cases | Very High | Testing | Tan Tran | 12 | 2011-12-13 | 5 | 5 | 50
8 | Document Architecture Driver Document- Quality Attribute | High | Architecture | Tan Tran | 15 | 2012-01-08 | 20 | 16 | 100
9 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tan Tran | 16 | 2012-01-13 | 35 | 34 | 100
10 | Design database | Medium | Architecture | Tan Tran | 17 | 2012-01-21 | 15 | 22.5 | 100
11 | Document SAD | Very High | Architecture | Tan Tran | 17 | 2012-01-16 | 35 | 32.5 | 100
12 | Review SAD | High | Architecture | Tan Tran | 17 | 2012-01-18 | 5 | 3 | 100
13 | Risk analysis in implementation | Very High | Management | Tan Tran | 17 | 2012-01-17 | 6 | 6.5 | 100
14 | Programming "Manage Catalog" | Very High | Implementation | Tan Tran | 18 | 2012-01-26 | 140 | 159 | 100
15 | Programming "Manage Detail Information Management" | Very High | Implementation | Tan Tran | 23 | 2012-03-27 | 16 | 16 | 100
16 | Programming "Employee Code Setting" | Very High | Implementation | Tan Tran | 23 | 2012-03-27 | 8 | 7 | 100
18 | Programming "Certificate Setting" | Very High | Implementation | Tan Tran | 25 | 2012-03-31 | 9 | 8 | 100
20 | Testing | Very High | Implementation | Tan Tran | 25 | 2012-03-30 | 24 | 20 | 50
17 | Programming "Column Setting" | Very High | Implementation | Tan Tran | 26 | 2012-03-28 | 8 | 8 | 100
19 | Programming "Employee Report" | Very High | Implementation | Tan Tran | 31 | 2012-04-28 | 24 | 24 | 100
|  | Week | 2 | 3 | 5 | 6 | 9 | 12 | 15 | 16 | 17 | 18 | 23 | 25 | 26 | 31
|  | Estimated hour | 8 | 6 | 16 | 5 | 3 | 5 | 20 | 35 | 61 | 70 | 24 | 33 | 8 | 24
|  | Actual hour | 2 | 4 | 24 | 3 | 4.5 | 5 | 16 | 34 | 64.5 | 65 | 23 | 28 | 8 | 24

## Tuong Nguyen
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Documenting the report | Low | Architecture | Tuong Nguyen | 2 | 2011-10-08 | 2 | 2 | 100
2 | Research ACDM for architecture process | Medium | Architecture | Tuong Nguyen | 3 | 2011-10-10 | 8 | 6.5 | 100
3 | Research about the CoOp & Scenario | Medium | RE | Tuong Nguyen | 3 | 2011-10-15 | 1 | 1.5 | 100
4 | Update Plan for Architecture Phase | Medium | Architecture | Tuong Nguyen | 4 | 2011-10-23 | 2 | 3 | 100
5 | Update Process, Assumption & Milestone for Architecture | Medium | Architecture | Tuong Nguyen | 4 | 2011-10-23 | 2 | 1 | 100
6 | Training entity framework and WCF | High | Architecture | Tuong Nguyen | 4 | 2011-10-21 | 4 | 3 | 100
7 | Document Scenarios for "Training Management" | Low | RE | Tuong Nguyen | 5 | 2011-10-25 | 1 | 2 | 100
8 | Research the forms provided by customer | Low | RE | Tuong Nguyen | 5 | 2011-10-26 | 1 | 1 | 100
9 | Concept Operation | Very High | RE | Tuong Nguyen | 6 | 2011-11-04 | 7 | 5 | 100
10 | Prepare for Architecture Driver | Medium | Architecture | Tuong Nguyen | 6 | 2011-11-03 | 2 | 3 | 100
11 | Discover Architecture Driver | Medium | Architecture | Tuong Nguyen | 6 | 2011-11-03 | 10 | 14.5 | 100
12 | Training for interface | Medium | Implementation | Tuong Nguyen | 6 | 2011-11-05 | 8 | 6 | 100
13 | Writing Use case + Description | Medium | RE | Tuong Nguyen | 7 | 2011-11-09 | 12 | 9.5 | 100
14 | Document Architecture Driver | High | Architecture | Tuong Nguyen | 7 | 2011-11-09 | 11 | 13 | 100
15 | Write Architecture Design | Very High | Architecture | Tuong Nguyen | 9 | 2011-11-24 | 6 | 5.5 | 100
16 | Training design interface | Medium | Architecture | Tuong Nguyen | 9 | 2011-11-26 | 4 | 3 | 100
17 | Design System Context | Medium | Architecture | Tuong Nguyen | 10 | 2011-12-31 | 4 | 2 | 100
18 | Review Architecture Driver | Low | Architecture | Tuong Nguyen | 11 | 2011-12-09 | 2 | 3.5 | 100
19 | Program "Recruitment Job" Interface | Medium | Implementation | Tuong Nguyen | 12 | 2011-12-11 | 2 | 2 | 100
20 | Update Architecture Driver | High | Architecture | Tuong Nguyen | 12 | 2011-12-12 | 7 | 11 | 100
21 | Research tactic for performance and modify | Medium | Architecture | Tuong Nguyen | 12 | 2011-12-16 | 5 | 4 | 100
22 | Design dynamic view | High | Architecture | Tuong Nguyen | 12 | 2011-12-11 | 4 | 3 | 100
23 | Update Design decision, design rationale | Medium | Architecture | Tuong Nguyen | 12 | 2011-12-16 | 5 | 6.5 | 100
25 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tuong Nguyen | 13 | 2011-12-19 | 5 | 3.5 | 100 | 2011-09-26
27 | Update Static, Dynamic, and Behavior Diagram | Medium | Architecture | Tuong Nguyen | 13 | 2011-12-19 | 3 | 2 | 100
28 | Research about N-Tier | Medium | Architecture | Tuong Nguyen | 13 | 2011-12-19 | 1.5 | 1 | 100
29 | Review SRS | Medium | RE | Tuong Nguyen | 13 | 2011-12-19 | 1 | 1.5 | 100
30 | Document Architecture Design | High | Architecture | Tuong Nguyen | 13 | 2011-12-21 | 35 | 31 | 100
31 | Design Database | High | Architecture | Tuong Nguyen | 15 | 2012-01-08 | 6 | 5.5 | 50
32 | Programming "Reward Management" | Very High | Implementation | Tuong Nguyen | 27 | 2012-03-27 | 8 | 5 | 100
33 | Programming "Penalty Management" | Very High | Implementation | Tuong Nguyen | 27 | 2012-03-30 | 8 | 6 | 100
36 | Programming "Communist Party Management" | Very High | Testing | Tuong Nguyen | 27 | 2012-04-06 | 30 | 27 | 100
35 | Programming "Lecture Position Management" | Very High | Implementation | Tuong Nguyen | 28 | 2012-04-06 | 8 | 6 | 100
34 | Testing | Very High | Implementation | Tuong Nguyen | 29 | 2012-04-10 | 20 | 28 | 50
|  | Week | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 15 | 27 | 28 | 29
|  | Estimated hour | 2 | 9 | 8 | 2 | 22 | 22 | 10 | 4 | 2 | 23 | 45.5 | 6 | 46 | 8 | 8
|  | Actual hour | 2 | 8 | 7 | 3 | 24.5 | 22.5 | 8.5 | 3 | 3.5 | 26.5 | 39 | 5.5 | 38 | 6 | 28

## Loc Phan
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Write document content for meeting with customer | Medium | RE | Loc Phan | 1 | 2011-10-03 | 5 | 3 | 100 | 2011-10-01
2 | List questions for meeting with customer | High | RE | Loc Phan | 1 | 2011-10-03 | 5 | 4 | 100
3 | Research about Design Process | Medium | RE | Loc Phan | 1 | 2011-10-05 | 5 | 5 | 100
4 | List questions and answer for meeting with customer | Medium | RE | Loc Phan | 1 | 2011-10-05 | 3 | 2 | 100
5 | Document list questions and answer | High | RE | Loc Phan | 1 | 2011-10-06 | 2 | 4 | 100
6 | Write introduction for ConceptOperation | Low | RE | Loc Phan | 1 | 2011-10-07 | 2 | 2 | 100
7 | Update part 6 for ConceptOperation | High | RE | Loc Phan | 5 | 2011-10-30 | 5 | 3 | 100
8 | Update part 3 for ConceptOperation | High | RE | Loc Phan | 5 | 2011-10-31 | 2 | 2 | 100
9 | Group catalog (from customer requirement) | Medium | RE | Loc Phan | 5 | 2011-11-01 | 2 | 2 | 100
10 | List informations to manage and group its. | Medium | RE | Loc Phan | 5 | 2011-11-04 | 2 | 1.5 | 100
11 | Document SRS part 2.5; 2.6; 2.7 | High | RE | Loc Phan | 6 | 2011-11-07 | 4 | 5 | 100
12 | Draw context Diagram and descript context | Medium | RE | Loc Phan | 6 | 2011-11-08 | 4 | 3 | 100
13 | Update Funtional Requirement and Business Rule | High | RE | Loc Phan | 7 | 2011-11-15 | 6 | 7 | 100
14 | Descript Use-case | High | RE | Loc Phan | 8 | 2011-11-24 | 8 | 8 | 100
15 | Update 2.3, 2.4, 2.6 , 2.7, 5 SRS and Functionlist. | High | RE | Loc Phan | 10 | 2011-12-05 | 3 | 4 | 100
16 | Update All use-case | High | RE | Loc Phan | 11 | 2011-12-11 | 4 | 5 | 100
17 | Draw activities diagram | Medium | RE | Loc Phan | 11 | 2011-12-15 | 5 | 6 | 100
18 | Update activities diagram | Medium | RE | Loc Phan | 11 | 2011-12-16 | 2 | 3 | 100
19 | Update Risk Register | Medium | RE | Loc Phan | 12 | 2011-12-18 | 3 | 3 | 100
20 | Programming "Science Research" | Very High | Implementation | Loc Phan | 26 | 2012-03-30 | 8 | 12 | 100
21 | Programming "Mobilization" | Very High | Implementation | Loc Phan | 27 | 2012-03-31 | 8 | 6 | 100
22 | Programming "Syllabus" | Very High | Implementation | Loc Phan | 27 | 2012-04-01 | 8 | 6 | 100
23 | Programming "Staff Internship" | Very High | Implementation | Loc Phan | 27 | 2012-04-03 | 8 | 6 | 100
| Fix code | Very High | Implementation | Loc Phan | 28 | 2012-04-12 | 8 | 6 | 100
24 | Testing | Very High | Testing | Loc Phan | 30 | 2012-04-24 | 16 | 6 | 50
|  | Week | 1 | 5 | 6 | 7 | 8 | 10 | 11 | 12
|  | Estimated hour | 22 | 12 | 5 | 6 | 8 | 6 | 8 | 2
|  | Actual hour | 20 | 13 | 3 | 5.5 | 8 | 7 | 8 | 3

## Nhung Huynh
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research about Risk Management Process and Template | High | Management | Nhung Huynh | 3 | 2011-10-11 | 7 | 6 | 100
2 | Doc risk management plan and create template | High | Management | Nhung Huynh | 3 | 2011-10-13 | 5 | 5.5 | 100
3 | Doc Concep Operation | Very High | RE | Nhung Huynh | 7 | 2011-11-07 | 15 | 10.5 | 50
4 | Review and fix Concept Operation document | Very High | RE | Nhung Huynh | 11 | 2011-12-11 | 11 | 10 | 50
5 | Implement Interface: Extend Information and Detail Information | High | Management | Nhung Huynh | 11 | 2011-12-11 | 5 | 4 | 50
6 | Add and review Risk category | Medium | Management | Nhung Huynh | 12 | 2011-12-12 | 4 | 2.5 | 100
7 | Doc Functional Requirement in SRS, business rules | Very High | RE | Nhung Huynh | 12 | 2011-12-12 | 3 | 1.5 | 50
8 | Review and fix SRS | Very High | RE | Nhung Huynh | 12 | 2011-12-12 | 2 | 1.5 | 50
9 | Doc Project Plan | Very High | Management | Nhung Huynh | 13 | 2011-12-23 | 35 | 35 | 100
10 | Doc Detail Plan | Very High | Management | Nhung Huynh | 13 | 2011-12-23 | 6 | 6 | 100
11 | Add new Risk category | Medium | Management | Nhung Huynh | 13 | 2011-12-19 | 1 | 1 | 100
12 | Doc InformationCategory in Concept Operation | Medium | Management | Nhung Huynh | 15 | 2012-01-02 | 13 | 12.5 | 50
13 | Doc artifact about Change Management Plan | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
14 | Research about Change management | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
15 | Report and doc Change management log and Change Request for CR01 | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
16 | Doc Weekly report for mentor | Medium | Management | Nhung Huynh | 21 | 2012-02-15 | 42 | 42 | 100
17 | Research about rule for team member | Very High | Management | Nhung Huynh | 21 | 2012-02-15 | 5 | 5 | 100
18 | Research about team 360 review on web | High | Management | Nhung Huynh | 21 | 2012-02-15 | 8 | 8 | 100
19 | Programming "Task notenook" | Very High | Implementation | Nhung Huynh | 25 | 2012-03-17 | 8 | 8 | 100
20 | Programming "Trainning Course" | Very High | Implementation | Nhung Huynh | 25 | 2012-03-21 | 8 | 13 | 100
21 | Programming "Lecture Probation" | Very High | Implementation | Nhung Huynh | 25 | 2012-03-20 | 8 | 9 | 100
22 | Programming "Family Relationship" | Very High | Implementation | Nhung Huynh | 25 | 2012-03-16 | 16 | 22.5 | 100
23 | Testing | Very High | Testing | Nhung Huynh | 26 | 2012-03-26 | 60 | 19 | 50
|  | Week | 3 | 7 | 11 | 12 | 13 | 15 | 16 | 21
|  | Estimated hour | 12 | 15 | 16 | 9 | 42 | 13 | 12 | 55
|  | Actual hour | 11.5 | 10.5 | 14 | 5.5 | 42 | 12.5 | 12 | 55

## Quyet Nguyen
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research system function | Medium | RE | Quyet Nguyen | 2 | 2011-10-04 | 2 | 3 | 50 | 2011-09-26
2 | Establish RE process | High | RE | Quyet Nguyen | 2 | 2011-10-08 | 5 | 8 | 100
3 | Draw overview for finding and understanding system | High | RE | Quyet Nguyen | 2 | 2011-10-06 | 1 | 3 | 100
4 | Meeting with customers for confirming information after team are analyze customers 's information. | High | RE | Quyet Nguyen | 2 | 2011-10-04 | 3 | 3 | 50
5 | Meeting with customers for reflecting business process | High | RE | Quyet Nguyen | 2 | 2011-10-07 | 3 | 3 | 50
6 | Fix Digram HRM | High | RE | Quyet Nguyen | 3 | 2011-10-13 | 3 | 2 | 100
7 | Analyze system | High | RE | Quyet Nguyen | 3 | 2011-10-14 | 2 | 2.5 | 100
8 | Draw business process | High | RE | Quyet Nguyen | 4 | 2011-10-19 | 8 | 6 | 100
9 | Scenario HRM Concept document | High | RE | Quyet Nguyen | 4 | 2011-10-22 | 3 | 4 | 100
10 | Reparing and Reviewing with customers | High | RE | Quyet Nguyen | 5 | 2011-10-27 | 15 | 10 | 100
11 | Research some catagolue information | Medium | RE | Quyet Nguyen | 5 | 2011-10-25 | 2 | 2 | 100
12 | Review Catagoloue and Issue in Meeting | High | RE | Quyet Nguyen | 5 | 2011-10-29 | 2 | 2 | 100
13 | Meeting with customers for getting list information | High | RE | Quyet Nguyen | 5 | 2011-10-28 | 3 | 3 | 50
14 | Research SRS document | Medium | RE | Quyet Nguyen | 6 | 2011-10-31 | 10 | 7 | 100
15 | Update Overview SRS document | High | RE | Quyet Nguyen | 7 | 2011-11-07 | 2 | 3 | 100
16 | Meeting with customers for getting list information | High | RE | Quyet Nguyen | 9 | 2011-11-26 | 1 | 2 | 50
17 | Meeting with customers for finishing business process | High | RE | Quyet Nguyen | 10 | 2011-11-29 | 3 | 3 | 100
18 | Meeting with customers for adding fuction such as Manage Army Rank, Manage Labor Union, Manage Union Task, Manage Communist Party Task. | High | RE | Quyet Nguyen | 10 | 2011-11-29 | 3 | 3 | 50
19 | Meeting with customers for completing list information | High | RE | Quyet Nguyen | 11 | 2011-12-08 | 3 | 3 | 100
20 | Meeting with customers for reviewing new fuctions. | High | RE | Quyet Nguyen | 12 | 2011-12-12 | 3 | 4 | 100
21 | Asking some information are questioning. | Medium | RE | Quyet Nguyen | 13 | 2011-12-19 | 2 | 1 | 100
22 | Updating Reflection pappers. | High | RE | Quyet Nguyen | 17 | 2012-01-16 | 6 | 3 | 100
23 | Updating requirement process in Project Plan | Very High | RE | Quyet Nguyen | 21 | 2012-02-15 | 6 | 5 | 100
24 | Programming"Training Result Information" | Very High | Implementation | Quyet Nguyen | 25 | 2012-03-18 | 10 | 23 | 100
25 | Programming "Article" | Very High | Implementation | Quyet Nguyen | 25 | 2012-03-17 | 12 | 10 | 100
26 | Programming "Work" | Very High | Implementation | Quyet Nguyen | 26 | 2012-03-24 | 5 | 12 | 100
27 | Programming "Master Thesis" | Very High | Implementation | Quyet Nguyen | 26 | 2012-03-10 | 12 | 21 | 100
28 | Programming "Other" | Very High | Implementation | Quyet Nguyen | 26 | 2012-03-22 | 4 | 6 | 100
29 | Testing | Very High | Testing | Quyet Nguyen | 33 | 2012-05-08 | 3 | 2 | 50
|  | Week | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 17 | 21
|  | Estimated hour | 14 | 5 | 11 | 22 | 10 | 2 | 1 | 6 | 3 | 3 | 2 | 6 | 6
|  | Actual hour | 20 | 4.5 | 10 | 17 | 7 | 3 | 2 | 6 | 3 | 4 | 1 | 3 | 5

## Tung Nguyen
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Prepare content for meeting with customer | Medium | RE | Tung Nguyen | 1 | 2011-10-03 | 4 | 1 | 100
2 | Write document content for meeting with customer | High | RE | Tung Nguyen | 1 | 2011-10-04 | 2 | 2 | 100
3 | Review List of Requirement | Low | RE | Tung Nguyen | 1 | 2011-10-06 | 3 | 2 | 100
4 | List questions and answer for meeting with customer | Medium | RE | Tung Nguyen | 1 | 2011-10-07 | 2 | 1 | 100
5 | Research about testing Process | High | Testing | Tung Nguyen | 2 | 2011-10-14 | 7 | 7 | 100
6 | Description Phases software testing | High | Testing | Tung Nguyen | 2 | 2011-10-11 | 4 | 3 | 100
7 | Create Test plan | Very High | Testing | Tung Nguyen | 3 | 2011-10-20 | 11 | 11 | 100
8 | Create Template Testing | High | Testing | Tung Nguyen | 4 | 2011-10-26 | 9 | 9 | 100
9 | Document Concept of Operation | Medium | RE | Tung Nguyen | 5 | 2011-10-29 | 5 | 5 | 100
10 | Update Concept of Operation (mục 7 và quá trình diễn biến lương | Medium | RE | Tung Nguyen | 5 | 2011-11-02 | 5 | 5 | 100
11 | Review HRM requirement | Medium | RE | Tung Nguyen | 5 | 2011-10-31 | 3 | 2 | 100
12 | Create HRM Testing process | Very High | Testing | Tung Nguyen | 6 | 2011-11-08 | 10 | 11 | 100
13 | Create Template Test case | Medium | Testing | Tung Nguyen | 7 | 2011-11-17 | 3 | 3 | 100
14 | Describe Use Case | High | RE | Tung Nguyen | 9 | 2011-11-29 | 8 | 8 | 100
15 | Update Template Testcase | Medium | Testing | Tung Nguyen | 9 | 2011-12-02 | 6 | 5 | 100
16 | List Risk for Testing | Medium | Testing | Tung Nguyen | 12 | 2011-12-17 | 2 | 2 | 100
17 | Write Test Case (System test Specification) | High | Testing | Tung Nguyen | 12 | 2011-12-22 | 4 | 3 | 100
18 | Update Testcase (System test Specification) | Medium | Testing | Tung Nguyen | 14 | 2012-01-06 | 5 | 4 | 100 | 2011-10-01
19 | Programming "Union" | Very High | Implementation | Tung Nguyen |  |  |  |  | 100
20 | Programming "Trade Union" | Very High | Implementation | Tung Nguyen |  |  |  |  | 100
21 | Testing | Very High | Testing | Tung Nguyen |  |  |  |  | 50
|  | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 12 | 14
|  | Estimated hour | 11 | 11 | 11 | 9 | 13 | 10 | 3 | 14 | 6 | 5
|  | Actual hour | 6 | 10 | 11 | 9 | 12 | 11 | 3 | 13 | 5 | 4

## Dang Nguyen
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Define Detail Design process | High | Detail Design | Dang Nguyen | 2 | 2011-10-03 | 2 | 3 | 100
2 | Doc Detail Design process | Low | Detail Design | Dang Nguyen | 2 | 2011-10-08 | 0.5 | 1 | 100
3 | Concept of Operation: document Proposed System or Situation | Very High | RE | Dang Nguyen | 3 | 2011-10-10 | 10 | 11.5 | 100
4 | Concept of Operation: document Current System or Situation | High | RE | Dang Nguyen | 4 | 2011-10-18 | 4 | 5 | 100
5 | Read, Review and Draw Form of customer | Medium | RE | Dang Nguyen | 4 | 2011-10-23 | 3 | 3 | 100
6 | Draw current system overview | High | RE | Dang Nguyen | 4 | 2011-10-23 | 6 | 7 | 100
7 | Test Plan: ENTRANCE & EXIT CRITERIA | High | Testing | Dang Nguyen | 6 | 2011-11-04 | 2 | 2 | 100
8 | Project .Plan: Project Quality Plan | High | Management | Dang Nguyen | 6 | 2011-11-05 | 1 | 1 | 100
9 | Describe Quality Attribute | High | RE | Dang Nguyen | 6 | 2011-11-01 | 6 | 9 | 100
10 | List Use Case | Medium | RE | Dang Nguyen | 7 | 2011-11-12 | 1.5 | 1.5 | 100
11 | draw Register the hour for teacher process | Medium | RE | Dang Nguyen | 7 | 2011-11-07 | 1 | 1 | 100
12 | rework: System feature | High | RE | Dang Nguyen | 10 | 2011-12-02 | 2 | 2 | 100
13 | design Detail Design template | Medium | Detail Design | Dang Nguyen | 10 | 2011-12-01 | 3 | 4 | 100
14 | Draw Use Case | High | RE | Dang Nguyen | 11 | 2011-12-09 | 6 | 7 | 100
15 | Describe Use Case | High | RE | Dang Nguyen | 12 | 2011-12-13 | 5 | 7 | 100
16 | review SRS | Medium | RE | Dang Nguyen | 12 | 2011-12-13 | 3 | 2.5 | 100
17 | Implement Interface: manage major | Medium | Implementation | Dang Nguyen | 12 | 2011-12-12 | 3 | 3 | 100
18 | review Use Case Description | Medium | RE | Dang Nguyen | 12 | 2011-12-13 | 1 | 1 | 100
19 | Plan Detail Design | High | Detail Design | Dang Nguyen | 12 | 2011-12-13 | 3 | 3 | 100
20 | Implement interface: Working Progress and Labor Union | Medium | Implementation | Dang Nguyen | 13 | 2011-12-19 | 7 | 7 | 100
21 | Test Case : Working Progress and Labor Union | Medium | Testing | Dang Nguyen | 13 | 2011-12-19 | 2 | 3 | 100
22 | Decribe Detail design Introduction | Low | Detail Design | Dang Nguyen | 15 | 2012-01-08 | 1 | 1 | 100
23 | Design Interface: Detail Information | Very High | Implementation | Dang Nguyen | 17 | 2012-02-15 | 46 | 88 | 100
24 | Design the HRM system | Very High | Implementation | Dang Nguyen |  | 2012-04-17 | 60 | 56 | 100
25 | Programming "Subject Management" | Very High | Implementation | Dang Nguyen | 18 | 2012-03-25 | 8 | 9 | 100
25 | Programming "Income Management" | Very High | Implementation | Dang Nguyen | 19 | 2012-03-29 | 8 | 12 | 100
26 | Programming "Facility Management" | Very High | Implementation | Dang Nguyen | 20 | 2012-04-05 | 8 | 12 | 100
27 | Programming "Salaryconcient Management" | Very High | Implementation | Dang Nguyen | 21 | 2012-04-10 | 8 | 6 | 100
|  | Week | 2 | 3 | 4 | 6 | 7 | 10 | 11 | 12 | 13 | 15 | 17 | 18 | 19 | 20 | 21 | 22
|  | Estimated hour | 2.5 | 10 | 13 | 9 | 2.5 | 5 | 6 | 15 | 9 | 1 | 46 | 18 | 8 | 30 | 8 | 16
|  | Actual hour | 4 | 11.5 | 15 | 12 | 2.5 | 6 | 7 | 16.5 | 10 | 1 | 88 | 17 | 12 | 36 | 6 | 14

## Nguyen Dinh
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Capture assuptions based on provided document | Medium | RE | Nguyen Dinh | 2 | 2011-10-03 | 7 | 4 | 100
2 | Research and do ConOps document | High | RE | Nguyen Dinh | 2 | 2011-10-05 | 5 | 3 | 100
3 | Review List of Requirement | Low | RE | Nguyen Dinh | 2 | 2011-10-06 | 4 | 3 | 100
4 | Create HRM requirement process | High | RE | Nguyen Dinh | 2 | 2011-10-07 | 2 | 2 | 100
5 | Create and update requirement process | Medium | RE | Nguyen Dinh | 3 | 2011-10-10 | 2 | 2 | 100
6 | Re-construct user's requirement and analysis map | Medium | RE | Nguyen Dinh | 3 | 2011-10-13 | 4 | 3 | 100
7 | Update section five | Medium | RE | Nguyen Dinh | 5 | 2011-10-27 | 1 | 1 | 100
8 | Update section seven | Medium | RE | Nguyen Dinh | 5 | 2011-10-30 | 2 | 2 | 100
9 | Review and fix some bugs on ConsOpt | Medium | RE | Nguyen Dinh | 6 | 2011-10-31 | 4 | 3.5 | 100
10 | Research and deploy SVN using google code for team | Very High | Management | Nguyen Dinh | 6 | 2011-11-05 | 2 | 1 | 100
11 | Create initial version for list of functional requirements, business rules, system features | High | RE | Nguyen Dinh | 7 | 2011-11-10 | 3 | 3 | 100
12 | Review dataflow diagram | Medium | RE | Nguyen Dinh | 7 | 2011-11-10 | 2 | 1 | 100
13 | Review UC diagram, list of functional requirements, system feature, business rules | Medium | RE | Nguyen Dinh | 8 | 2011-11-17 | 2 | 2 | 100
14 | Fix version for ConsOpt due to Configuration Management Plan | Low | RE | Nguyen Dinh | 8 | 2011-11-17 | 1 | 0.5 | 100
15 | Develop UC diagram | Medium | RE | Nguyen Dinh | 8 | 2011-11-20 | 4 | 3 | 100
16 | Review list of functional requirements | Medium | RE | Nguyen Dinh | 9 | 2011-11-21 | 2 | 1 | 100
17 | Create UC description template, write description for UC description | Medium | RE | Nguyen Dinh | 9 | 2011-11-22 | 2 | 1 | 100
18 | Write UC description for UC03.2.2.7 to UC03.2.2.11 | Medium | RE | Nguyen Dinh | 9 | 2011-11-24 | 6 | 5 | 100
19 | Update UC description for UC03.2.2.7 to UC03.2.2.11 | Medium | RE | Nguyen Dinh | 9 | 2011-11-27 | 2 | 2 | 100
20 | Review SRS | Medium | RE | Nguyen Dinh | 10 | 2011-11-29 | 1 | 1 | 100
21 | Update section 1 and fix some bugs on entire document | Medium | RE | Nguyen Dinh | 11 | 2011-12-06 | 2 | 2 | 100
22 | Update section 1 and 2.1, part of 2.2 | Medium | RE | Nguyen Dinh | 11 | 2011-12-07 | 1 | 1 | 100
23 | Update section 2 | Medium | RE | Nguyen Dinh | 11 | 2011-12-07 | 2 | 1 | 100
24 | Review and fix some bugs in system feature sheet | Low | RE | Nguyen Dinh | 11 | 2011-12-08 | 1 | 0.5 | 100
25 | Review 2.3, review and update 2.4, 2.5, 2.6 | Medium | RE | Nguyen Dinh | 11 | 2011-12-09 | 2 | 1 | 100
26 | Update 2.7 | Medium | RE | Nguyen Dinh | 12 | 2011-12-11 | 2 | 2 | 100
27 | Gather and translate content table of ConsOpt to English | Low | Management | Nguyen Dinh | 15 | 2012-01-08 | 1 | 0.5 | 100
28 | Add reflection paper: First version, plus introduction, architect, project management | Medium | Management | Nguyen Dinh | 16 | 2012-01-12 | 2 | 1 | 100
29 | Review and update requirement process: process description | Medium | RE | Nguyen Dinh | 22 | 2012-02-20 | 2 | 1 | 100
30 | Update personal measurement information | Low | Management | Nguyen Dinh | 23 | 2012-02-28 | 2 | 1 | 100
31 | Research about C# and Silverlight | Very High | Implementation | Nguyen Dinh | 11 | 2012-09-12 | 20 | 14 | 50
32 | Review and translate in to English Consopt | Medium | RE | Nguyen Dinh |  |  | 10 | 4 | 25
33 | Programming "Staff History", "Family Relationship", "Emulation", "Internal Trainning" | Very High | Implementation | Nguyen Dinh | 28 | 2012-06-04 | 24 | 123 | 100
34 | Testing | Very High | Implementation | Nguyen Dinh | 31 | 26/04/2012 | 24 | 3 | 100
|  |  | Week | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 22 | 23
|  |  | Estimated hour | 18 | 6 | 3 | 6 | 5 | 7 | 12 | 1 | 8 | 2 | 1 | 2 | 2 | 2
|  |  | Actual hour | 12 | 5 | 3 | 4.5 | 4 | 5.5 | 9 | 1 | 5.5 | 2 | 0.5 | 1 | 1 | 1

## PercentActualComplete
Percentage of actual task complete per estimated |  |  | (Actual Finish – Start)( Plan Finish – Start) /100%
Task | Start | Finish | Actual Start | Actual Finish | % work complete
Concept Operation | 2011-10-01 | 2011-12-12 | 2012-01-19 | 2012-01-21 | 80.64
SRS | 2011-10-31 | 2011-12-28 | 2011-11-11 | 2012-01-17 | 45.24
Architect Driver | 2011-11-01 | 2011-12-12 | 2011-11-04 | 2012-01-20 | 32.8
Architect Design | 2011-11-23 | 2011-12-29 | 2012-01-20 | 2012-02-11 | 28.8
Detail Design | 2011-12-13 | 2012-01-10 | 2012-03-10 | 2012-04-17 | 35.28
System test cases | 2011-12-22 | 2012-12-30 | 2012-02-11 | 2012-02-15 | 205.7
Integration test cases | 2012-01-02 | 2012-01-10 |  |  | -3272.8
Acceptance test | 2011-12-06 | 2011-12-14 | 2012-01-24 | 2012-01-27 | 4.16
System test | 2011-12-22 | 2011-12-30 | 2012-02-11 | 2012-02-15 | 4.4
Conduct System test | 2012-03-15 | 2012-03-16 | 2012-05-01 | 2012-05-05 | 0.51
Conduct Acceptance test | 2012-03-26 | 2012-03-28 | 2012-05-05 |  | -819.88
Conduct Integration test | 2012-03-15 | 2012-03-16 | 2012-03-06 | 2012-05-01 | 0.47
Programming | 2011-11-28 | 2012-03-14 | 2012-03-10 | 2012-04-28 | 162.64