## Sheet1
HRM Measurement
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research ACDM for architecture process | Medium | Architecture | Tan Tran | 2 | 2011-10-07 | 8 | 2 | 100 | 2011-09-26
2 | Document Concept of Operation | Medium | RE | Tan Tran | 3 | 2011-10-11 | 3 | 2.5 | 100
3 | Review HRM requirement | Medium | RE | Tan Tran | 3 | 2011-10-12 | 3 | 1.5 | 100
4 | Analyse Requirement - Draw mindmap of PIM | High | RE | Tan Tran | 5 | 2011-10-29 | 16 | 24 | 100
5 | Document project plan- Methodology Introduction | High | Management | Tan Tran | 9 | 2011-11-27 | 3 | 4.5 | 100
6 | Programming "Manage Catalog" | Very High | Implementation | Tan Tran | 18 | 2012-01-26 | 70 | 61 | 100
7 | Design database | Medium | Architecture | Tan Tran | 17 | 2012-01-21 | 15 | 22.5 | 100
8 | Document Architecture Driver Document- Quality Attribute | High | Architecture | Tan Tran | 15 | 2012-01-08 | 20 | 16 | 100
9 | Review ConsOpt | Medium | RE | Tan Tran | 6 | 2011-11-03 | 5 | 3 | 100
10 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tan Tran | 16 | 2012-01-13 | 35 | 20 | 100
11 | Document SAD | Very High | Architecture | Tan Tran | 17 | 2012-01-16 | 35 | 32.5 | 100
12 | Review SAD | High | Architecture | Tan Tran | 17 | 2012-01-18 | 5 | 3 | 100
13 | Risk analysis in implementation | Very High | Management | Tan Tran | 17 | 2012-01-17 | 6 | 6.5 | 100
14 | Write test cases | Very High | Testing | Tan Tran | 12 | 2011-12-13 | 5 | 5 | 50
15 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tuong Nguyen | 13 | 2011-12-19 | 5 | 3.5 | 100
16 | Research ACDM for architecture process | Medium | Architecture | Tuong Nguyen | 3 | 2011-10-10 | 8 | 6.5 | 100
17 | Document Scenarios for "Training Management" | Low | RE | Tuong Nguyen | 5 | 2011-10-25 | 1 | 2 | 100
18 | Concept Operation | Very High | RE | Tuong Nguyen | 6 | 2011-11-04 | 7 | 5 | 100
19 | Prepare for Architecture Driver | Medium | Architecture | Tuong Nguyen | 6 | 2011-11-03 | 2 | 3 | 100
20 | Update Architecture Driver | High | Architecture | Tuong Nguyen | 13 | 2011-12-25 | 4 | 5 | 50
21 | Design Database | High | Architecture | Tuong Nguyen | 15 | 2012-01-08 | 6 | 5.5 | 50
22 | Write Architecture Design | Very High | Architecture | Tuong Nguyen | 9 | 2011-11-24 | 6 | 5.5 | 100
23 | Program "Nghề nghiệp" Interface | Medium | Implementation | Tuong Nguyen | 11 | 2011-12-09 | 2 | 3.5 | 100
24 | Review SAD | Medium | Architecture | Tuong Nguyen | 11 | 2011-12-09 | 5 | 3.5 | 50
25 | Design System Context | Medium | Architecture | Tuong Nguyen | 14 | 2011-12-31 | 4 | 2 | 100
26 | Doc Project Plan | Very High | Management | Nhung Huynh | 13 | 2011-12-23 | 35 | 35 | 100
27 | Doc Detail Plan | Very High | Management | Nhung Huynh | 13 | 2011-12-23 | 6 | 6 | 100
28 | Doc Weekly report for mentor | Medium | Management | Nhung Huynh | 21 | 2012-02-15 | 42 | 42 | 100
29 | Research about rule for team member | Very High | Management | Nhung Huynh | 21 | 2012-02-15 | 5 | 5 | 100
30 | Research about team 360 review on web | High | Management | Nhung Huynh | 21 | 2012-02-15 | 8 | 8 | 100
31 | Research about Risk Management Process and Template | High | Management | Nhung Huynh | 3 | 2011-10-11 | 7 | 6 | 100
32 | Doc risk management plan and create template | High | Management | Nhung Huynh | 3 | 2011-10-13 | 5 | 5.5 | 100
33 | Add and review Risk category | Medium | Management | Nhung Huynh | 12 | 2011-12-12 | 4 | 2.5 | 100
34 | Doc Concep Operation | Very High | RE | Nhung Huynh | 7 | 2011-11-07 | 15 | 10.5 | 50
35 | Doc InformationCategory in Concept Operation | Medium | Management | Nhung Huynh | 15 | 2012-01-02 | 13 | 12.5 | 50
36 | Review and fix Concept Operation document | Very High | RE | Nhung Huynh | 11 | 2011-12-11 | 11 | 10 | 50
37 | Doc Functional Requirement in SRS, business rules | Very High | RE | Nhung Huynh | 12 | 2011-12-12 | 3 | 1.5 | 50
38 | Review and fix SRS | Very High | RE | Nhung Huynh | 12 | 2011-12-12 | 2 | 1.5 | 50
39 | Add new Risk category | Medium | Management | Nhung Huynh | 13 | 2011-12-19 | 1 | 1 | 100
40 | Implement Interface: Extend Information and Detail Information | High | Management | Nhung Huynh | 11 | 2011-12-11 | 5 | 4 | 50
41 | Doc artifact about Change Management Plan | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
42 | Research about Change management | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
43 | Report and doc Change management log and Change Request for CR01 | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
44 | Define Detail Design process | High | Detail Design | Dang Nguyen | -5830 |  | 2 | 1.5 | 100
45 | Doc Detail Design process | Low | Detail Design | Dang Nguyen | -5830 |  | 0.5 | 0.5 | 100
46 | Concept of Operation: document Proposed System or Situation | Very High | RE | Dang Nguyen | -5830 |  | 10 | 11.5 | 100
47 | Concept of Operation: document Current System or Situation | High | RE | Dang Nguyen | -5830 |  | 4 | 5 | 100
48 | Read, Review and Draw Form of customer | Medium | RE | Dang Nguyen | -5830 |  | 3 | 3 | 100
49 | Test Plan: ENTRANCE & EXIT CRITERIA | High | Testing | Dang Nguyen | -5830 |  | 2 | 2 | 100
50 | Project .Plan: Project Quality Plan | High | Management | Dang Nguyen | -5830 |  | 1 | 1 | 100
51 | Describe Quality Attribute | High | RE | Dang Nguyen | -5830 |  | 6 | 9 | 100
52 | draw current system overview | High | RE | Dang Nguyen | -5830 |  | 7 | 7 | 100
53 | List Use Case | Medium | RE | Dang Nguyen | -5830 |  | 1.5 | 1.5 | 100
54 | draw Register the hour for teacher process | Medium | RE | Dang Nguyen | -5830 |  | 1 | 1 | 100
55 | Draw Use Case | High | RE | Dang Nguyen | -5830 |  | 6 | 7 | 100
56 | Describe Use Case | High | RE | Dang Nguyen | -5830 |  | 5 | 7 | 100
57 | rework: System feature | High | RE | Dang Nguyen | -5830 |  | 2 | 2 | 100
58 | review SRS | Medium | RE | Dang Nguyen | -5830 |  | 3 | 2.5 | 100
59 | design Detail Design template | Medium | Detail Design | Dang Nguyen | -5830 |  | 3 | 4 | 100
60 | Implement Interface: manage major | Medium | Implementation | Dang Nguyen | -5830 |  | 3 | 3 | 100
61 | review Use Case Description | Medium | RE | Dang Nguyen | -5830 |  | 1 | 1 | 100
62 | Plan Detail Design | High | Detail Design | Dang Nguyen | -5830 |  | 3 | 3 | 100
63 | Decribe Detail design Introduction | Low | Detail Design | Dang Nguyen | -5830 |  | 1 | 1 | 100
64 | Implement interface: Working Progress and Labor Union | Medium | Implementation | Dang Nguyen | -5830 |  | 7 | 7 | 100
65 | Test Case : Working Progress and Labor Union | Medium | Testing | Dang Nguyen | -5830 |  | 2 | 3 | 100
66 | Design Interface: Detail Information | Very High | Implementation | Dang Nguyen | -5830 |  | 12 | 9 | 70
67 | Write document content for meeting with customer | Medium | RE | Loc Phan | 1 | 2011-09-30 | 5 | 3 | 100
68 | List questions for meeting with customer | High | RE | Loc Phan | 1 | 2011-09-30 | 5 | 4 | 100
69 | Research about Design Process | Medium | RE | Loc Phan | 2 | 2011-10-05 | 5 | 5 | 100
70 | List questions and answer for meeting with customer | Medium | RE | Loc Phan | 2 | 2011-10-05 | 3 | 2 | 100
71 | Document list questions and answer | High | RE | Loc Phan | 2 | 2011-10-06 | 2 | 4 | 100
72 | Write introduction for ConceptOperation | Low | RE | Loc Phan | 2 | 2011-10-07 | 2 | 2 | 100
73 | Update part 6 for ConceptOperation | High | RE | Loc Phan | 5 | 2011-10-30 | 5 | 3 | 100
74 | Update part 3 for ConceptOperation | High | RE | Loc Phan | 6 | 2011-10-31 | 2 | 2 | 100
75 | Group catalog (from customer requirement) | Medium | RE | Loc Phan | 6 | 2011-11-01 | 2 | 2 | 100
76 | List informations to manage and group its. | Medium | RE | Loc Phan | 6 | 2011-11-04 | 4 | 1.5 | 100
77 | Document SRS part 2.5; 2.6; 2.7 | High | RE | Loc Phan | 7 | 2011-11-07 | 4 | 5 | 100
78 | Draw context Diagram and descript context | Medium | RE | Loc Phan | 7 | 2011-11-08 | 4 | 3 | 100
79 | Update Funtional Requirement and Business Rule | High | RE | Loc Phan | 8 | 2011-11-15 | 4 | 7 | 100
80 | Descript Use-case | High | RE | Loc Phan | 9 | 2011-11-24 | 6 | 8 | 100
81 | Update 2.3, 2.4, 2.6 , 2.7, 5 SRS and Functionlist. | High | RE | Loc Phan | 11 | 2011-12-05 | 3 | 4 | 100
82 | Update All use-case | High | RE | Loc Phan | 11 | 2011-12-11 | 4 | 5 | 100
83 | Update Risk Register | Medium | RE | Loc Phan | 12 | 2011-12-18 | 3 | 3 | 100
84 | Draw activities diagram | Medium | RE | Loc Phan | 19 | 2012-02-02 | 5 | 6 | 100
85 | Update activities diagram | Medium | RE | Loc Phan | 10 | 2011-12-02 | 2 | 3 | 100
86 | Prepare content for meeting with customer | Medium | RE | Tung Nguyen | 2 | 2011-10-03 |  | 1 | 100
87 | Write document content for meeting with customer | High | RE | Tung Nguyen | 2 | 2011-10-04 |  | 2 | 100
88 | Review List of Requirement | Low | RE | Tung Nguyen | 2 | 2011-10-06 |  | 2 | 100
89 | Research about testing Process | High | Testing | Tung Nguyen | 3 | 2011-10-14 |  | 7 | 100
90 | List questions and answer for meeting with customer | Medium | RE | Tung Nguyen | 2 | 2011-10-07 |  | 1 | 100
91 | Create HRM Testing process | Very High | Testing | Tung Nguyen | 7 | 2011-11-08 |  | 11 | 100
92 | Description Phases software testing | High | Testing | Tung Nguyen | 3 | 2011-10-11 |  | 3 | 100
93 | Create Test plan | Very High | Testing | Tung Nguyen | 4 | 2011-10-20 |  | 11 | 100
94 | Create Template Testing | High | Testing | Tung Nguyen | 5 | 2011-10-26 |  | 9 | 100
95 | Document Concept of Operation | Medium | RE | Tung Nguyen | 5 | 2011-10-29 |  | 5 | 100
96 | Review HRM requirement | Medium | RE | Tung Nguyen | 6 | 2011-10-31 |  | 2 | 100
97 | Describe Use Case | High | RE | Tung Nguyen | 10 | 2011-11-29 |  | 8 | 100
98 | Create Template Test case | Medium | Testing | Tung Nguyen | 8 | 2011-11-17 |  | 3 | 100
99 | Update Template Testcase | Medium | Testing | Tung Nguyen | 10 | 2011-12-02 |  | 5 | 100
100 | Write Test Case | High | Testing | Tung Nguyen | 13 | 2011-12-22 |  | 3 | 100
101 | List Risk for Testing | Medium | Testing | Tung Nguyen | 12 | 2011-12-17 |  | 2 | 100
102 | Reparing and Reviewing with customers | High | RE | Quyet Nguyen | 5 | 2011-10-27 | 15 | 10 | 100
103 | Updating requirement process in Project Plan | Very High | RE | Quyet Nguyen | 21 | 2012-02-15 | 6 | 5 | 100
104 | Updating Reflection pappers. | High | RE | Quyet Nguyen | 17 | 2012-01-16 | 6 | 3 | 100
105 | Research SRS document | Medium | RE | Quyet Nguyen | 6 | 2011-10-31 | 10 | 7 | 100
106 | Research some catagolue information | Medium | RE | Quyet Nguyen | 5 | 2011-10-25 | 2 | 2 | 100
107 | Review Catagoloue and Issue in Meeting | High | RE | Quyet Nguyen | 5 | 2011-10-29 | 2 | 2 | 100
108 | Draw business process | High | RE | Quyet Nguyen | 4 | 2011-10-19 | 8 | 6 | 100
109 | Update Overview SRS document | High | RE | Quyet Nguyen | -10 | 2011-07-11 | 2 | 3 | 100
111 | Research system function | Medium | RE | Quyet Nguyen | 2 | 2011-10-04 | 2 | 3 | 50
112 | Establish RE process | High | RE | Quyet Nguyen | 2 | 2011-10-08 | 5 | 8 | 100
113 | Draw overview for finding and understanding system | High | RE | Quyet Nguyen | 2 | 2011-10-06 | 1 | 3 | 100
114 | Fix Digram HRM | High | RE | Quyet Nguyen | 3 | 2011-10-13 | 3 | 2 | 100
115 | Analyze system | High | RE | Quyet Nguyen | 3 | 2011-10-14 | 2 | 2.5 | 100
116 | Scenario HRM Concept document | High | RE | Quyet Nguyen | 4 | 2011-10-22 | 3 | 4 | 100
118 | Meeting with customers for confirming information after team are analyze customers 's information. | High | RE | Quyet Nguyen | 2 | 2011-10-04 | 3 | 3 | 50
119 | Meeting with customers for reflecting business process | High | RE | Quyet Nguyen | 2 | 2011-10-07 | 3 | 3 | 50
120 | Meeting with customers for getting list information | High | RE | Quyet Nguyen | 5 | 2011-10-28 | 3 | 3 | 50
121 | Meeting with customers for finishing business process | High | RE | Quyet Nguyen | 10 | 2011-11-29 | 3 | 3 | 100
122 | Meeting with customers for getting list information | High | RE | Quyet Nguyen | 9 | 2011-11-26 | 1 | 2 | 50
123 | Meeting with customers for completing list information | High | RE | Quyet Nguyen | 11 | 2011-12-08 |  | 3 | 100
124 | Meeting with customers for adding fuction such as Manage Army Rank, Manage Labor Union, Manage Union Task, Manage Communist Party Task. | High | RE | Quyet Nguyen | 10 | 2011-11-29 | 3 | 3 | 50
125 | Meeting with customers for reviewing new fuctions. | High | RE | Quyet Nguyen | 12 | 2011-12-12 | 3 | 4 | 100
126 | Asking some information are questioning. | Medium | RE | Quyet Nguyen | 13 | 2011-12-19 | 2 | 1 | 100
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180

## Tan Tran
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research ACDM for architecture process | Medium | Architecture | Tan Tran | 2 | 2011-10-07 | 8 | 2 | 100 | 2011-09-26
2 | Document Concept of Operation | Medium | RE | Tan Tran | 3 | 2011-10-11 | 3 | 2.5 | 100
3 | Review HRM requirement | Medium | RE | Tan Tran | 3 | 2011-10-12 | 3 | 1.5 | 100
4 | Analyse Requirement - Draw mindmap of PIM | High | RE | Tan Tran | 5 | 2011-10-29 | 16 | 24 | 100
5 | Review ConsOpt | Medium | RE | Tan Tran | 6 | 2011-11-03 | 5 | 3 | 100
6 | Document project plan- Methodology Introduction | High | Management | Tan Tran | 9 | 2011-11-27 | 3 | 4.5 | 100
7 | Write test cases | Very High | Testing | Tan Tran | 12 | 2011-12-13 | 5 | 5 | 50
8 | Document Architecture Driver Document- Quality Attribute | High | Architecture | Tan Tran | 15 | 2012-01-08 | 20 | 16 | 100
9 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tan Tran | 16 | 2012-01-13 | 35 | 34 | 100
10 | Design database | Medium | Architecture | Tan Tran | 17 | 2012-01-21 | 15 | 22.5 | 100
11 | Document SAD | Very High | Architecture | Tan Tran | 17 | 2012-01-16 | 35 | 32.5 | 100
12 | Review SAD | High | Architecture | Tan Tran | 17 | 2012-01-18 | 5 | 3 | 100
13 | Risk analysis in implementation | Very High | Management | Tan Tran | 17 | 2012-01-17 | 6 | 6.5 | 100
14 | Programming "Manage Catalog" | Very High | Implementation | Tan Tran | 18 | 2012-01-26 | 70 | 65 | 100
|  | Week | 2 | 3 | 5 | 6 | 9 | 12 | 15 | 16 | 17 | 18
|  | Estimated hour | 8 | 6 | 16 | 5 | 3 | 5 | 20 | 35 | 61 | 70
|  | Actual hour | 2 | 4 | 24 | 3 | 4.5 | 5 | 16 | 34 | 64.5 | 65

## Tuong Nguyen
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
11 | Documenting the report | Low | Architecture | Tuong Nguyen | 2 | 2011-10-08 | 2 | 2 | 100
1 | Research ACDM for architecture process | Medium | Architecture | Tuong Nguyen | 3 | 2011-10-10 | 8 | 6.5 | 100
13 | Research about the CoOp & Scenario | Medium | RE | Tuong Nguyen | 3 | 2011-10-15 | 1 | 1.5 | 100
12 | Update Plan for Architecture Phase | Medium | Architecture | Tuong Nguyen | 4 | 2011-10-23 | 2 | 3 | 100
14 | Update Process, Assumption & Milestone for Architecture | Medium | Architecture | Tuong Nguyen | 4 | 2011-10-23 | 2 | 1 | 100
16 | Training entity framework and WCF | High | Architecture | Tuong Nguyen | 4 | 2011-10-21 | 4 | 3 | 100
2 | Document Scenarios for "Training Management" | Low | RE | Tuong Nguyen | 5 | 2011-10-25 | 1 | 2 | 100
15 | Research the forms provided by customer | Low | RE | Tuong Nguyen | 5 | 2011-10-26 | 1 | 1 | 100
3 | Concept Operation | Very High | RE | Tuong Nguyen | 6 | 2011-11-04 | 7 | 5 | 100
4 | Prepare for Architecture Driver | Medium | Architecture | Tuong Nguyen | 6 | 2011-11-03 | 2 | 3 | 100
17 | Discover Architecture Driver | Medium | Architecture | Tuong Nguyen | 6 | 2011-11-03 | 10 | 14.5 | 100
18 | Training for interface | Medium | Implementation | Tuong Nguyen | 6 | 2011-11-05 | 3 | 2 | 100
19 | Writing Use case + Description | Medium | RE | Tuong Nguyen | 7 | 2011-11-09 | 12 | 9.5 | 100
30 | Document Architecture Driver | High | Architecture | Tuong Nguyen | 7 | 2011-11-09 | 11 | 13 | 100
5 | Write Architecture Design | Very High | Architecture | Tuong Nguyen | 9 | 2011-11-24 | 6 | 5.5 | 100
20 | Training design interface | Medium | Architecture | Tuong Nguyen | 9 | 2011-11-26 | 4 | 3 | 100
9 | Design System Context | Medium | Architecture | Tuong Nguyen | 10 | 2011-12-31 | 4 | 2 | 100
21 | Review Architecture Driver | Low | Architecture | Tuong Nguyen | 11 | 2011-12-09 | 2 | 3.5 | 100
6 | Program "Recruitment Job" Interface | Medium | Implementation | Tuong Nguyen | 12 | 2011-12-11 | 2 | 2 | 100
8 | Update Architecture Driver | High | Architecture | Tuong Nguyen | 12 | 2011-12-12 | 7 | 11 | 100
22 | Research tactic for performance and modify | Medium | Architecture | Tuong Nguyen | 12 | 2011-12-16 | 5 | 4 | 100
23 | Design dynamic view | High | Architecture | Tuong Nguyen | 12 | 2011-12-11 | 4 | 3 | 100
24 | Update Design decision, design rationale | Medium | Architecture | Tuong Nguyen | 12 | 2011-12-16 | 5 | 6.5 | 100
25 | Make the interface for "Family Relationship Management" | Medium | Implementation | Tuong Nguyen | 12 | 2011-12-17 | 3 | 2.5 | 100
7 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tuong Nguyen | 13 | 2011-12-19 | 5 | 3.5 | 100 | 2011-09-26
26 | Make the interface for "Union Task Management" | Medium | Implementation | Tuong Nguyen | 13 | 2011-12-18 | 2 | 1.5 | 100
27 | Update Static, Dynamic, and Behavior Diagram | Medium | Architecture | Tuong Nguyen | 13 | 2011-12-19 | 3 | 2 | 100
28 | Research about N-Tier | Medium | Architecture | Tuong Nguyen | 13 | 2011-12-19 | 1.5 | 1 | 100
29 | Review SRS | Medium | RE | Tuong Nguyen | 13 | 2011-12-19 | 1 | 1.5 | 100
31 | Document Architecture Design | High | Architecture | Tuong Nguyen | 13 | 2011-12-21 | 35 | 31 | 100
10 | Design Database | High | Architecture | Tuong Nguyen | 15 | 2012-01-08 | 6 | 5.5 | 50
|  | Week | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 15
|  | Estimated hour | 2 | 9 | 8 | 2 | 22 | 22 | 10 | 4 | 2 | 26 | 47.5 | 6
|  | Actual hour | 2 | 8 | 7 | 3 | 24.5 | 22.5 | 8.5 | 3 | 3.5 | 29 | 40.5 | 5.5

## Loc Phan
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Write document content for meeting with customer | Medium | RE | Loc Phan | 1 | 2011-09-30 | 5 | 3 | 100
2 | List questions for meeting with customer | High | RE | Loc Phan | 1 | 2011-09-30 | 5 | 4 | 100
3 | Research about Design Process | Medium | RE | Loc Phan | 2 | 2011-10-05 | 5 | 5 | 100
4 | List questions and answer for meeting with customer | Medium | RE | Loc Phan | 2 | 2011-10-05 | 3 | 2 | 100
5 | Document list questions and answer | High | RE | Loc Phan | 2 | 2011-10-06 | 2 | 4 | 100
6 | Write introduction for ConceptOperation | Low | RE | Loc Phan | 2 | 2011-10-07 | 2 | 2 | 100
7 | Update part 6 for ConceptOperation | High | RE | Loc Phan | 5 | 2011-10-30 | 5 | 3 | 100
8 | Update part 3 for ConceptOperation | High | RE | Loc Phan | 6 | 2011-10-31 | 2 | 2 | 100
9 | Group catalog (from customer requirement) | Medium | RE | Loc Phan | 6 | 2011-11-01 | 2 | 2 | 100
10 | List informations to manage and group its. | Medium | RE | Loc Phan | 6 | 2011-11-04 | 2 | 1.5 | 100
11 | Document SRS part 2.5; 2.6; 2.7 | High | RE | Loc Phan | 7 | 2011-11-07 | 4 | 5 | 100
12 | Draw context Diagram and descript context | Medium | RE | Loc Phan | 7 | 2011-11-08 | 4 | 3 | 100
13 | Update Funtional Requirement and Business Rule | High | RE | Loc Phan | 8 | 2011-11-15 | 6 | 7 | 100
14 | Descript Use-case | High | RE | Loc Phan | 9 | 2011-11-24 | 8 | 8 | 100
15 | Update 2.3, 2.4, 2.6 , 2.7, 5 SRS and Functionlist. | High | RE | Loc Phan | 11 | 2011-12-05 | 3 | 4 | 100
16 | Update All use-case | High | RE | Loc Phan | 11 | 2011-12-11 | 4 | 5 | 100
17 | Update Risk Register | Medium | RE | Loc Phan | 12 | 2011-12-18 | 3 | 3 | 100
18 | Draw activities diagram | Medium | RE | Loc Phan | 19 | 2012-02-02 | 5 | 6 | 100
19 | Update activities diagram | Medium | RE | Loc Phan | 10 | 2011-12-02 | 2 | 3 | 100
|  | Week | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 19
|  | Estimated hour | 10 | 12 | 5 | 6 | 8 | 6 | 8 | 2 | 7 | 3 | 5
|  | Actual hour | 7 | 13 | 3 | 5.5 | 8 | 7 | 8 | 3 | 9 | 3 | 6

## Nhung Huynh
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research about Risk Management Process and Template | High | Management | Nhung Huynh | 3 | 2011-10-11 | 7 | 6 | 100
2 | Doc risk management plan and create template | High | Management | Nhung Huynh | 3 | 2011-10-13 | 5 | 5.5 | 100
3 | Doc Concep Operation | Very High | RE | Nhung Huynh | 7 | 2011-11-07 | 15 | 10.5 | 50
4 | Review and fix Concept Operation document | Very High | RE | Nhung Huynh | 11 | 2011-12-11 | 11 | 10 | 50
5 | Implement Interface: Extend Information and Detail Information | High | Management | Nhung Huynh | 11 | 2011-12-11 | 5 | 4 | 50
6 | Add and review Risk category | Medium | Management | Nhung Huynh | 12 | 2011-12-12 | 4 | 2.5 | 100
7 | Doc Functional Requirement in SRS, business rules | Very High | RE | Nhung Huynh | 12 | 2011-12-12 | 3 | 1.5 | 50
8 | Review and fix SRS | Very High | RE | Nhung Huynh | 12 | 2011-12-12 | 2 | 1.5 | 50
9 | Doc Project Plan | Very High | Management | Nhung Huynh | 13 | 2011-12-23 | 35 | 35 | 100
10 | Doc Detail Plan | Very High | Management | Nhung Huynh | 13 | 2011-12-23 | 6 | 6 | 100
11 | Add new Risk category | Medium | Management | Nhung Huynh | 13 | 2011-12-19 | 1 | 1 | 100
12 | Doc InformationCategory in Concept Operation | Medium | Management | Nhung Huynh | 15 | 2012-01-02 | 13 | 12.5 | 50
13 | Doc artifact about Change Management Plan | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
14 | Research about Change management | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
15 | Report and doc Change management log and Change Request for CR01 | High | Management | Nhung Huynh | 16 | 2012-01-13 | 4 | 4 | 100
16 | Doc Weekly report for mentor | Medium | Management | Nhung Huynh | 21 | 2012-02-15 | 42 | 42 | 100
17 | Research about rule for team member | Very High | Management | Nhung Huynh | 21 | 2012-02-15 | 5 | 5 | 100
18 | Research about team 360 review on web | High | Management | Nhung Huynh | 21 | 2012-02-15 | 8 | 8 | 100
|  | Week | 3 | 7 | 11 | 12 | 13 | 15 | 16 | 21
|  | Estimated hour | 12 | 15 | 16 | 9 | 42 | 13 | 12 | 55
|  | Actual hour | 11.5 | 10.5 | 14 | 5.5 | 42 | 12.5 | 12 | 55

## Quyet Nguyen
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research system function | Medium | RE | Quyet Nguyen | 2 | 2011-10-04 | 2 | 3 | 50 | 2011-09-26
2 | Establish RE process | High | RE | Quyet Nguyen | 2 | 2011-10-08 | 5 | 8 | 100
3 | Draw overview for finding and understanding system | High | RE | Quyet Nguyen | 2 | 2011-10-06 | 1 | 3 | 100
4 | Meeting with customers for confirming information after team are analyze customers 's information. | High | RE | Quyet Nguyen | 2 | 2011-10-04 | 3 | 3 | 50
5 | Meeting with customers for reflecting business process | High | RE | Quyet Nguyen | 2 | 2011-10-07 | 3 | 3 | 50
6 | Fix Digram HRM | High | RE | Quyet Nguyen | 3 | 2011-10-13 | 3 | 2 | 100
7 | Analyze system | High | RE | Quyet Nguyen | 3 | 2011-10-14 | 2 | 2.5 | 100
8 | Draw business process | High | RE | Quyet Nguyen | 4 | 2011-10-19 | 8 | 6 | 100
9 | Scenario HRM Concept document | High | RE | Quyet Nguyen | 4 | 2011-10-22 | 3 | 4 | 100
10 | Reparing and Reviewing with customers | High | RE | Quyet Nguyen | 5 | 2011-10-27 | 15 | 10 | 100
11 | Research some catagolue information | Medium | RE | Quyet Nguyen | 5 | 2011-10-25 | 2 | 2 | 100
12 | Review Catagoloue and Issue in Meeting | High | RE | Quyet Nguyen | 5 | 2011-10-29 | 2 | 2 | 100
13 | Meeting with customers for getting list information | High | RE | Quyet Nguyen | 5 | 2011-10-28 | 3 | 3 | 50
14 | Research SRS document | Medium | RE | Quyet Nguyen | 6 | 2011-10-31 | 10 | 7 | 100
15 | Update Overview SRS document | High | RE | Quyet Nguyen | 7 | 2011-11-07 | 2 | 3 | 100
16 | Meeting with customers for getting list information | High | RE | Quyet Nguyen | 9 | 2011-11-26 | 1 | 2 | 50
17 | Meeting with customers for finishing business process | High | RE | Quyet Nguyen | 10 | 2011-11-29 | 3 | 3 | 100
18 | Meeting with customers for adding fuction such as Manage Army Rank, Manage Labor Union, Manage Union Task, Manage Communist Party Task. | High | RE | Quyet Nguyen | 10 | 2011-11-29 | 3 | 3 | 50
19 | Meeting with customers for completing list information | High | RE | Quyet Nguyen | 11 | 2011-12-08 | 3 | 3 | 100
20 | Meeting with customers for reviewing new fuctions. | High | RE | Quyet Nguyen | 12 | 2011-12-12 | 3 | 4 | 100
21 | Asking some information are questioning. | Medium | RE | Quyet Nguyen | 13 | 2011-12-19 | 2 | 1 | 100
22 | Updating Reflection pappers. | High | RE | Quyet Nguyen | 17 | 2012-01-16 | 6 | 3 | 100
23 | Updating requirement process in Project Plan | Very High | RE | Quyet Nguyen | 21 | 2012-02-15 | 6 | 5 | 100
|  | Week | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 17 | 21
|  | Estimated hour | 14 | 5 | 11 | 22 | 10 | 2 | 1 | 6 | 3 | 3 | 2 | 6 | 6
|  | Actual hour | 20 | 4.5 | 10 | 17 | 7 | 3 | 2 | 6 | 3 | 4 | 1 | 3 | 5

## Tung Nguyen
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Prepare content for meeting with customer | Medium | RE | Tung Nguyen | 2 | 2011-10-03 | 4 | 1 | 100
2 | Write document content for meeting with customer | High | RE | Tung Nguyen | 2 | 2011-10-04 | 2 | 2 | 100
3 | Review List of Requirement | Low | RE | Tung Nguyen | 2 | 2011-10-06 | 3 | 2 | 100
4 | List questions and answer for meeting with customer | Medium | RE | Tung Nguyen | 2 | 2011-10-07 | 2 | 1 | 100
5 | Research about testing Process | High | Testing | Tung Nguyen | 3 | 2011-10-14 | 7 | 7 | 100
6 | Description Phases software testing | High | Testing | Tung Nguyen | 3 | 2011-10-11 | 4 | 3 | 100
7 | Create Test plan | Very High | Testing | Tung Nguyen | 4 | 2011-10-20 | 11 | 11 | 100
8 | Create Template Testing | High | Testing | Tung Nguyen | 5 | 2011-10-26 | 9 | 9 | 100
9 | Document Concept of Operation | Medium | RE | Tung Nguyen | 5 | 2011-10-29 | 5 | 5 | 100
10 | Review HRM requirement | Medium | RE | Tung Nguyen | 6 | 2011-10-31 | 3 | 2 | 100
11 | Create HRM Testing process | Very High | Testing | Tung Nguyen | 7 | 2011-11-08 | 10 | 11 | 100
12 | Create Template Test case | Medium | Testing | Tung Nguyen | 8 | 2011-11-17 | 3 | 3 | 100
13 | Describe Use Case | High | RE | Tung Nguyen | 10 | 2011-11-29 | 8 | 8 | 100
14 | Update Template Testcase | Medium | Testing | Tung Nguyen | 10 | 2011-12-02 | 6 | 5 | 100
15 | List Risk for Testing | Medium | Testing | Tung Nguyen | 12 | 2011-12-17 | 2 | 2 | 100
16 | Write Test Case | High | Testing | Tung Nguyen | 13 | 2011-12-22 | 4 | 3 | 100
|  | Week | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 10 | 12 | 13
|  | Estimated hour | 11 | 11 | 11 | 14 | 3 | 10 | 3 | 14 | 2 | 4
|  | Actual hour | 6 | 10 | 11 | 14 | 2 | 11 | 3 | 13 | 2 | 3

## Dang Nguyen
No. | Task | Priority | Phase | Assign to | Week | Finished date | Estimated hour | Actual hour | Percent complete
1 | Define Detail Design process | High | Detail Design | Dang Nguyen | 2 | 2011-10-03 | 2 | 1.5 | 100
2 | Doc Detail Design process | Low | Detail Design | Dang Nguyen | 2 | 2011-10-08 | 0.5 | 0.5 | 100
3 | Concept of Operation: document Proposed System or Situation | Very High | RE | Dang Nguyen | 3 | 2011-10-10 | 10 | 11.5 | 100
4 | Concept of Operation: document Current System or Situation | High | RE | Dang Nguyen | 4 | 2011-10-18 | 4 | 5 | 100
5 | Read, Review and Draw Form of customer | Medium | RE | Dang Nguyen | 4 | 2011-10-23 | 3 | 3 | 100
6 | draw current system overview | High | RE | Dang Nguyen | 4 | 2011-10-23 | 7 | 7 | 100
7 | Test Plan: ENTRANCE & EXIT CRITERIA | High | Testing | Dang Nguyen | 6 | 2011-11-04 | 2 | 2 | 100
8 | Project .Plan: Project Quality Plan | High | Management | Dang Nguyen | 6 | 2011-11-05 | 1 | 1 | 100
9 | Describe Quality Attribute | High | RE | Dang Nguyen | 6 | 2011-11-01 | 6 | 9 | 100
10 | List Use Case | Medium | RE | Dang Nguyen | 7 | 2011-11-12 | 1.5 | 1.5 | 100
11 | draw Register the hour for teacher process | Medium | RE | Dang Nguyen | 7 | 2011-11-07 | 1 | 1 | 100
12 | rework: System feature | High | RE | Dang Nguyen | 10 | 2011-12-02 | 2 | 2 | 100
13 | design Detail Design template | Medium | Detail Design | Dang Nguyen | 10 | 2011-12-01 | 3 | 4 | 100
14 | Draw Use Case | High | RE | Dang Nguyen | 11 | 2011-12-09 | 6 | 7 | 100
15 | Describe Use Case | High | RE | Dang Nguyen | 12 | 2011-12-13 | 5 | 7 | 100
16 | review SRS | Medium | RE | Dang Nguyen | 12 | 2011-12-13 | 3 | 2.5 | 100
17 | Implement Interface: manage major | Medium | Implementation | Dang Nguyen | 12 | 2011-12-12 | 3 | 3 | 100
18 | review Use Case Description | Medium | RE | Dang Nguyen | 12 | 2011-12-13 | 1 | 1 | 100
19 | Plan Detail Design | High | Detail Design | Dang Nguyen | 12 | 2011-12-13 | 3 | 3 | 100
20 | Implement interface: Working Progress and Labor Union | Medium | Implementation | Dang Nguyen | 13 | 2011-12-19 | 7 | 7 | 100
21 | Test Case : Working Progress and Labor Union | Medium | Testing | Dang Nguyen | 13 | 2011-12-19 | 2 | 3 | 100
22 | Decribe Detail design Introduction | Low | Detail Design | Dang Nguyen | 15 | 2012-01-08 | 1 | 1 | 100
23 | Design Interface: Detail Information | Very High | Implementation | Dang Nguyen | 17 | 2012-01-16 | 12 | 9 | 70
|  | Week | 2 | 3 | 4 | 6 | 7 | 10 | 11 | 12 | 13 | 15 | 17
|  | Estimated hour | 2.5 | 10 | 14 | 9 | 2.5 | 5 | 6 | 15 | 9 | 1 | 12
|  | Actual hour | 2 | 11.5 | 15 | 12 | 2.5 | 6 | 7 | 16.5 | 10 | 1 | 9

## Sheet2
Síp | 6.5
Tan | 2.5
Tung | 5
Loc | 7
Dang | 16.5