## Sheet1
HRM Measurement
No. | Task | Priority | Phase | Assign to | Finished date | Estimated hour | Actual hour | Percent complete
1 | Research ACDM for architecture process | Medium | Architecture | Tan Tran | 2011-07-10 | 8 | 2 | 100
2 | Document Concept of Operation | Medium | RE | Tan Tran |  | 3 | 2.5 | 100
3 | Review HRM requirement | Medium | RE | Tan Tran |  | 3 | 1.5 | 100
4 | Analyse Requirement - Draw mindmap of PIM | High | RE | Tan Tran |  | 16 | 24 | 100
5 | Document project plan- Methodology Introduction | High | Management | Tan Tran |  | 3 | 4.5 | 100
6 | Programming "Manage Catalog" | Very High | Implementation | Tan Tran |  | 70 | 45.5 | 50
7 | Review use case | Medium | RE | Tan Tran |  | 6 | 2 | 50
8 | Design database- Manage Catalog | Medium | Architecture | Tan Tran |  | 15 | 6.5 | 50
9 | Document Architecture Driver Document- Quality Attribute | High | Architecture | Tan Tran |  | 20 | 14 | 50
10 | Review ConsOpt | Medium | RE | Tan Tran |  | 5 | 3 | 100
11 | Reseach about MVVM+WCF RIA Service | High | Architecture | Tan Tran |  | 35 | 8 | 50
12 | Document SAD | Very High | Architecture | Tan Tran |  | 35 | 11 | 50
13 | Review SAD | High | Architecture | Tan Tran |  | 35 | 1.5 | 50
14 | Risk analysis in implementation | Very High | Management | Tan Tran |  | 6 | 6.5 | 100
15 | Write test cases | Very High | Testing | Tan Tran |  | 42 | 5 | 50
16 | Research about the MVVM pattern, WCF | High | Architecture | Tuong Nguyen |  | 5 | 3.5 | 100
17 | Research about the ACDM | Medium | Architecture | Tuong Nguyen |  | 8 | 6.5 | 100
18 | Document Snarios for "Đào tạo" | Low | RE | Tuong Nguyen |  | 1 | 2 | 100
19 | Concept Operation | Very High | RE | Tuong Nguyen |  | 7 | 5 | 100
20 | Prepare for Architecture Driver | Medium | Architecture | Tuong Nguyen | 2011-03-11 | 2 | 3 | 100
21 | Update Architecture Driver | High | Architecture | Tuong Nguyen |  | 4 | 5 | 50
22 | Design Database | High | Architecture | Tuong Nguyen |  | 6 | 3 | 50
23 | Write Architecture Design | Very High | Architecture | Tuong Nguyen |  | 6 | 5.5 | 100
24 | Program "Nghề nghiệp" Interface | Medium | Implementation | Tuong Nguyen | 2011-09-12 | 2 | 3.5 | 100
25 | Review Architecture driver | Medium | Architecture | Tuong Nguyen |  | 5 | 3.5 | 50
26 | Design System Context | Medium | Architecture | Tuong Nguyen |  | 4 | 2 | 100
27 | Doc Project Plan | Very High | Management | Nhung Huyng |  | 35 | 35 | 100
28 | Doc Detail Plan | Very High | Management | Nhung Huyng |  | 6 | 6 | 100
29 | Doc Weekly report for mentor | Medium | Management | Nhung Huyng |  | 42 | 42 | 100
30 | Research about rule for team member | Very High | Management | Nhung Huyng |  | 5 | 5 | 100
31 | Research about team 360 review on web | High | Management | Nhung Huyng |  | 8 | 8 | 100
32 | Research about Risk Management Process and Template | High | Management | Nhung Huyng | 2011-11-10 | 7 | 6 | 100
33 | Doc risk management plan and create template | High | Management | Nhung Huyng | 13/10/2011 | 5 | 5.5 | 100
34 | Add and review Risk category | Medium | Management | Nhung Huyng | 2011-12-12 | 4 | 2.5 | 100
35 | Doc Concep Operation | Very High | RE | Nhung Huyng | 2011-07-11 | 15 | 10.5 | 50
36 | Doc InformationCategory in Concept Operation | Medium | Management | Nhung Huyng | 2012-02-01 | 13 | 12.5 | 50
37 | Review and fix Concept Operation document | Very High | RE | Nhung Huyng | 2011-11-12 | 11 | 10 | 50
38 | Doc Functional Requirement in SRS, business rules | Very High | RE | Nhung Huyng | 2011-12-12 | 3 | 1.5 | 50
39 | Review and fix SRS | Very High | RE | Nhung Huyng | 2011-12-12 | 2 | 1.5 | 50
40 | Add new Risk category | Medium | Management | Nhung Huyng | 19/12/2011 | 1 | 1 | 100
41 | Implement Interface: Extend Information and Detail Information | High | Management | Nhung Huyng | 2011-11-12 | 5 | 4 | 50
42 | Doc artifact about Change Management Plan | High | Management | Nhung Huyng | 13/1/2012 | 4 | 4 | 100
43 | Research about Change management | High | Management | Nhung Huyng | 13/1/2012 | 4 | 4 | 100
44 | Report and doc Change management log and Change Request for CR01 | High | Management | Nhung Huyng | 13/1/2012 | 4 | 4 | 100
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207